## Product Backlog
ID | Epic | Backlog Item | Priority | SP | First | Second | Acceptance Criteria | Dependency | Sprint | Status | Description | Linked Requirement | Evidence Required
Mj01 | Project Management | Confirm the four-person group | P0 | 1 | T | Y | Approval from the tutor is recorded in writing and stored in the repository. | - | S1 | Partly done | The brief expects five people. Ask the tutor to approve four, and keep the reply. --- v16.0 status note: Tutor approval for a four-person group was given, but the reply itself is not held in the repository, which is what the acceptance criterion asks for. It must be attached before the submission is marked complete. | Assessment brief, section 1 - group size | bpm/docs/15-project-plan-assessment.md section 6 (group size and roles)
Mj02 | Project Management | Agree scope, stakeholders and assumptions | P0 | 5 | T | D | A stakeholder list, a scope boundary and a numbered assumption list are agreed by all four. | - | S1 | Done | Read the case study together and agree what we build, who is involved, and what we are guessing. | Case study, closing paragraph | bpm/docs/04-modelling-decisions.md section 6 (numbered assumptions and scope boundary)
Mj03 | Project Management | Product backlog and Definition of Done | P0 | 5 | T | Y | Every item has a first owner, a second owner, an estimate, acceptance conditions and a dependency. | Mj02 | S1 | Done | Write the full list of work, and agree what 'finished' means on this project. | Brief section 2 - prioritised backlog, shared Definition of Done | docs/GroupMj Product-Backlog.xlsx (this workbook); bpm/docs/07-product-backlog.md section 6 (Definition of Done)
Mj04 | Project Management | Sprint 1 plan | P0 | 3 | T | Y | A written Sprint goal and a Sprint 1 backlog exist, and the estimate fits our capacity. | Mj03 | S1 | Done | Agree the Sprint 1 goal, how much we can take on, and which items we commit to. | Brief section 2 - each Sprint agrees a goal and a controlled Sprint backlog | docs/GroupMj Sprint-1-Backlog.xlsx; bpm/docs/07-product-backlog.md section 5.1
Mj05 | Project Management | Prepare and record standup 1 (SU1) | P0 | 2 | T | Y | All four members have a written update covering progress, evidence, next step, blocker and handover. | Mj04 | S1 | Done (record reconstructed) | Every member prepares a short update with evidence before the graded standup. | Brief section 2 - graded standups; attendance alone scores nothing | bpm/docs/19-standups.md section 'Stand-up 1'
Mj06 | Project Management | Sprint 1 review demo and snapshot | P0 | 5 | T | Y | The BPMN increment runs end to end in front of the tutor, and tag sr1-snapshot is pushed. | Mj04 | S1 | Done | Demonstrate what actually runs at the end of Sprint 1, and freeze that version. | Brief sections 2 and 4 - SR1 is marked on the increment as it stands | bpm/docs/10-sprint-reviews-and-feedback.md section 1 and section 2; repository tag sr1-snapshot
Mj07 | Project Management | Sprint 1 retrospective | P0 | 2 | T | Y | At least two improvements are agreed, each with an owner and a target Sprint. | Mj06 | S1 | Done | Short meeting after the review: what worked, what did not, what we change next Sprint. | Brief section 2 - retrospective after each review | bpm/docs/10-sprint-reviews-and-feedback.md section 2 (Retrospective 1)
Mj08 | Project Management | Sprint 2 plan | P0 | 3 | T | Y | The Sprint 2 goal refers to specific SR1 feedback, and the backlog reflects it. | Mj07 | S2 | Done | Turn the Sprint 1 feedback into a Sprint 2 goal and backlog. | Brief section 2 - feedback from each review must shape the next Sprint | docs/GroupMj Sprint-2-Backlog.xlsx; bpm/docs/07-product-backlog.md section 5.2
Mj09 | Project Management | Prepare and record standup 2 (SU2) | P0 | 2 | T | Y | All four members have a written update, including any handover. | Mj08 | S2 | Done (record reconstructed) | Same as SU1, and each member also reports on any handover that happened. | Brief - personal progress, next actions and handover evidence | bpm/docs/19-standups.md section 'Stand-up 2'
Mj10 | Project Management | Sprint 2 review (SR2) | P0 | 8 | T | Y | BPMN, workers and forms run together in one demonstration, and tag sr2-snapshot is pushed. | Mj08 | S2 | Done | Present the integrated increment to the tutor and collect feedback. | Brief section 2 - SR2 is marked on the integrated increment | bpm/docs/10-sprint-reviews-and-feedback.md section 3 and section 4; repository tag sr2-snapshot
Mj11 | Requirements | Functional requirements list | P0 | 8 | Y | D | Every requirement has an ID and can be traced to the process step that satisfies it. | Mj02 | S1 | Done | Write the numbered functional requirements the system must satisfy, taken from the case study. | Case study - the closing section asks for functional and non-functional requirements | bpm/docs/07-product-backlog.md section 4 (Linked Requirement column of this workbook)
Mj12 | Requirements | Non-functional requirements | P0 | 5 | Y | T | Each requirement states how it can be tested, not just what it asks for. | Mj11 | S2 | Done | Rules about security, audit trails, availability and accessibility, rather than features. | Case study - access control, audit records, availability, patient accessibility | bpm/docs/07-product-backlog.md section 9; bpm/docs/09-risk-contingency-and-config-management.md
Mj13 | Requirements | Data and variable dictionary | P0 | 5 | L | D | Every worker input and output appears in the dictionary, and names match the models exactly. | Mj11 | S1 | Done | List every process variable: its name, type, where it comes from and which task uses it. | Brief - process variables must be exchanged correctly between forms, tasks and workers | bpm/tools/spec_v3.py check_gateway_variables; bpm/model/forms/ (237 field keys)
Mj14 | Requirements | External service interface definitions | P0 | 5 | L | T | Each service has a named input, a named output, and at least one defined failure response. | Mj11 | S1 | Done | Define what we send to and expect back from each simulated external service. | Brief task 02 - explain any simulated external service and its limitations | bpm/workers/DEPLOYMENT.md section 5 (simulated external services and their interfaces)
Mj15 | BPMN | Multi-pool collaboration diagram | P0 | 5 | L | T | Every participant named in the case study appears in a pool, and each pool has an owner. | Mj13 | S1 | Done | Lay out the participants as separate pools and show the messages that pass between them. | Brief task 01 - use multiple pools where independent participants collaborate | bpm/model/UFCEP6-0-3_Hospital_Patient_Pathway_v16.bpmn (7 participants); bpm/docs/17-single-pool-operational-model.md
Mj16 | BPMN | Referral intake and document check | P0 | 8 | T | D | The model requests missing documents and records the request, and never lets the secretary accept a referral. | Mj15 | S1 | Done | Model what the secretary does: check the referral pack is complete, and chase what is missing. | Case study - the secretary checks completeness but cannot judge clinical suitability | bpm/model/UFCEP6-0-3_Hospital_Patient_Pathway_v16.bpmn; bpm/model/forms/check-referral-pack.form; bpm/screenshots/run-v16-incomplete-pack.log
Mj17 | BPMN | Consultant clinical review | P0 | 8 | T | D | All four outcomes are reachable, and the record shows the reason and the consultant's identity. | Mj16 | S1 | Done | Model the four decisions a consultant can make, and record who decided and why. | Case study - accept, reject, request information or redirect; reason and decision maker must be recorded | bpm/model/forms/review-referral.form; bpm/screenshots/run-v16-happy-path.log; bpm/docs/04-modelling-decisions.md section 3
Mj18 | BPMN | New patient appointment booking | P0 | 13 | D | L | Both notification paths work, every contact attempt is recorded, and no appointment is confirmed without a slot. | Mj17 | S1 | Done | Model booking against the external scheduling service, including notification by letter and phone. | Case study - use the external scheduling service; phone as well as letter when the appointment is within two weeks | bpm/model/forms/choose-appointment-slot.form; bpm/screenshots/run-v16-no-capacity.log
Mj19 | BPMN | Consent and authorised treatment request | P0 | 8 | Y | D | The process blocks any treatment request that has not been authorised by a clinical role. | Mj18 | S1 | Done | Model recording consent, then creating a treatment request only a clinician can authorise. | Case study - treatment requests must be completed and authorised by a clinical professional | bpm/model/forms/record-consent-and-treatment-request.form; bpm/screenshots/run-v16-declined-treatment.log
Mj20 | BPMN | Treatment appointment coordination | P0 | 13 | Y | L | The pending path runs end to end, and repeating the attempt never creates a second booking. | Mj19 | S1 | Done | Model coordinating treatment slots, including what happens when an external service is unavailable. | Case study - hold pending, notify, record retries, and do not create a duplicate booking | bpm/model/forms/choose-appointment-slot.form; bpm/screenshots/run-v16-compensation.log
Mj21 | BPMN | Funding check and approval | P0 | 8 | T | L | All three funding outcomes are reachable and each approval records the four required fields. | Mj20 | S2 | Done | Work out who pays: the hospital, an insurer, or the patient, and record the approval details. | Case study - record the funding body, authorisation number, approved amount and any restrictions | bpm/model/forms/determine-funding-route.form; bpm/screenshots/run-v16-happy-path.log
Mj22 | BPMN | Payment process | P0 | 13 | D | L | Each failure outcome can be produced, and a retry never produces a second charge. | Mj21 | S2 | Done | Model taking payment through the external provider, including every way it can go wrong. | Case study - declined, cancelled, duplicate and never-completed payments; never charge twice | bpm/screenshots/run-v16-refund.log; bpm/workers/README.md (payment workers, no card data)
Mj23 | BPMN | Refund process | P1 | 8 | L | T | The model prevents a clinical-only role from approving a refund. | Mj22 | S2 | Done | Model refunds when treatment is cancelled or changed, approved only by finance. | Case study - finance decides refunds; clinical staff cannot approve them without finance authority | bpm/model/forms/decide-refund.form; bpm/screenshots/run-v16-no-refund.log
Mj24 | BPMN | Chemotherapy cycles and treatment changes | P1 | 8 | T | D | A change requested outside the system cannot be processed, and the clinical outcome is recorded. | Mj20 | S2 | Done | Model the review before each cycle, and the formal process for changing a treatment plan. | Case study - clinical review and blood tests before each cycle; changes need a formal authorised request, not an email | bpm/model/forms/review-chemotherapy-cycle.form; bpm/screenshots/run-v16-compensation.log
Mj25 | BPMN | Outpatient letter and escalation | P0 | 13 | T | D | All three escalation levels are reachable and the timer dates can be demonstrated. | Mj19 | S2 | Done | Model writing, approving and sending the letter, and chasing it when it is late. | Case study - letter within seven days; weekly reminder; escalate at one month and three months | bpm/model/forms/review-outstanding-correspondence.form; bpm/docs/03-test-record.md section J13-J14
Mj26 | BPMN | Follow-up, cancellation and no-show | P1 | 8 | L | D | If no slot matches the clinical timeframe, the case is flagged rather than quietly booked late. | Mj25 | S2 | Done | Model follow-up requests, and what happens when a patient cancels, refuses or does not attend. | Case study - record the event, decide the next step, and refer paid appointments to finance | bpm/model/forms/review-appointment-availability.form; bpm/screenshots/run-v16-no-capacity.log
Mj27 | BPMN | Enquiry classification and routing | P1 | 8 | D | T | A clinical enquiry cannot be closed by a non-clinical role, and every enquiry has a resolution record. | Mj19 | S2 | Done | Model logging a patient enquiry and routing it to admin, finance or clinical. | Case study - the telephone team must not give clinical advice; record time, handler and outcome | bpm/model/forms/log-enquiry.form; bpm/screenshots/run-v16-enquiry.log
Mj28 | BPMN | BPMN configuration, deployment and variable mapping | P0 | 5 | L | T | Every model deploys without error, and the variable names match the data dictionary. | Mj15-27 | S1/S2 | Done | Make the models deployable and check the variables line up across models, forms and workers. | Brief task 01 - configure the model for deployment | bpm/tools/deploy.sh; bpm/camunda/application.yaml; bpm/workers/src/main/resources/application.yaml
Mj29 | Workers | External scheduling worker | P0 | 8 | L | Y | Given a specialty and priority, it returns at least one slot or a clear 'none available' result. | Mj14 | S1 | Done | A small program that asks the scheduling service for an available slot. | Brief task 02 - workers fetch work, use input variables and return results | bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/tasks/SchedulingFindAppointmentSlotsWorker.java; bpm/workers/README.md
Mj30 | Workers | External communication worker | P0 | 5 | L | Y | The worker returns a delivery status, and a failed call is recorded without stopping the process. | Mj14 | S1 | Done | A worker that sends the letter and records the outcome of a telephone call. | Case study - every contact attempt and its outcome must be recorded | bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/tasks/CorrespondenceDispatchLetterWorker.java; bpm/workers/README.md
Mj31 | Workers | External payment worker | P0 | 13 | L | Y | The worker returns all four fields, and no card number is written to a log or a variable. | Mj14 | S2 | Done | A worker that sends a payment request and returns the provider's answer. | Case study - the provider returns status, reference, date and amount; no full card details | bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/tasks/PaymentProcessTransactionWorker.java; bpm/workers/README.md
Mj32 | Workers | Laboratory and imaging worker | P1 | 8 | L | Y | The worker returns either a result or an 'unavailable' response, and both are handled. | Mj14 | S2 | Done | A worker that simulates ordering a test and getting a result back. | Case study - blood tests before each chemotherapy cycle | bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/tasks/ExternalResourcesCheckAvailabilityWorker.java; bpm/workers/README.md
Mj33 | Workers | Error handling, retry and idempotency | P0 | 8 | L | Y | Invalid input and timeout are handled, and running the same job twice produces one booking. | Mj29-32 | S2 | Partly done | Make the workers behave sensibly when something goes wrong, and never act twice on the same job. --- v16.0 status note: Fail-fast behaviour, retry and idempotency are implemented and now exercised on six failure paths (bpm/docs/03-test-record.md K3). Not met: an invalid treatment request is refused by a job failure and an incident rather than by the TREATMENT_REQUEST_UNAUTHORISED business error the model declares (K5.9), and the scheduling recovery path has no retry bound (K5.8). | Case study - retry without creating a duplicate booking or a duplicate charge | bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/AbstractHospitalWorker.java (fail vs BPMN error); bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/config/SimulatedFailureRegistry.java
Mj34 | Workers | Worker configuration and secret template | P0 | 3 | L | Y | No credential appears in the source, and a new machine can be configured from the template alone. | Mj29 | S1 | Done | Keep connection settings and credentials out of the code. | Brief task 02 - provide configuration management evidence | bpm/workers/src/main/resources/application.yaml (environment-variable overrides); bpm/workers/README.md
Mj35 | Workers | Worker unit and integration tests | P0 | 8 | Y | L | Each worker has at least one passing test for normal and one for failure behaviour. | Mj29-33 | S2 | Partly done | Automated tests that prove each worker behaves correctly, including when things fail. --- v16.0 status note: 52 tests pass, covering DateRuleValidator, JobContext, AbstractHospitalWorker, NhsNumber, HospitalStore and AccessControl. Not met: the criterion asks for a test per worker, and none of the 38 execute() methods has one, nor is there an engine integration test. | Brief task 02 - provide evidence of appropriate testing | bpm/workers/src/test/java/ (52 tests); bpm/docs/08-test-plan.md section 7.2
Mj36 | Forms | Referral document check form | P0 | 5 | D | T | The form marks each document present or missing, and contains no field judging clinical suitability. | Mj16 | S1 | Done | The form the secretary fills in to record which documents arrived and which are missing. | Case study - the secretary can request missing information but cannot assess clinical suitability | bpm/model/forms/check-referral-pack.form; bpm/screenshots/v16/tasklist-form-rendered.png
Mj37 | Forms | Consultant review form | P0 | 5 | D | T | Decision and reason are mandatory, and the submitting user is captured. | Mj17 | S1 | Done | The form the consultant uses to record the decision, the reason and who they are. | Case study - reason and decision maker identity must be recorded | bpm/model/forms/review-referral.form; bpm/screenshots/tasklist-camunda-form.png
Mj38 | Forms | Appointment and contact record form | P0 | 8 | D | T | Multiple contact attempts can be recorded against one appointment. | Mj18 | S1 | Done | The form for priority, preferred window and the outcome of each contact attempt. | Case study - record every contact attempt and its result | bpm/model/forms/choose-appointment-slot.form; bpm/model/forms/record-telephone-contact-attempt.form
Mj39 | Forms | Treatment request form | P0 | 8 | D | T | All six fields are present and validated, and the form cannot be submitted without an authorising clinician. | Mj19 | S1 | Done | The form a clinician completes to authorise treatment. | Case study - the request states treatment, start date, cycles, frequency, reviews and special resources | bpm/model/forms/record-consent-and-treatment-request.form
Mj40 | Forms | Funding approval form | P0 | 5 | D | T | All four fields are captured, and the amount is validated as a positive number. | Mj21 | S2 | Done | The form finance completes to record who is paying and under what conditions. | Case study - record funding body, authorisation number, approved amount and restrictions | bpm/model/forms/determine-funding-route.form; bpm/model/forms/chase-funding-approval.form
Mj41 | Forms | Payment form and status | P0 | 8 | D | L | No field accepts a full card number, and the payment status is shown after submission. | Mj22 | S2 | Done | The payment screen. It must never ask for or store full card details. | Case study - the system must not store full card details | bpm/model/forms/decide-refund.form; bpm/workers/README.md (card-data refusal)
Mj42 | Forms | Treatment change form | P1 | 5 | D | T | The form captures the authorising clinician and the effect on existing costs. | Mj24 | S2 | Done | The formal form for changing a treatment plan, replacing email and phone requests. | Case study - changes requested by email or phone must not be processed | bpm/model/forms/review-treatment-change.form; bpm/model/forms/authorise-treatment-modification.form
Mj43 | Forms | Letter approval and admin check form | P0 | 8 | D | T | After clinical approval the clinical fields become read-only, and a letter can be sent back. | Mj25 | S2 | Done | Two steps in one screen: the consultant approves the clinical content, then the secretary checks the administration. | Case study - admin can fix formatting but cannot change clinical meaning; suspected clinical errors go back | bpm/model/forms/draft-clinic-letter.form; bpm/model/forms/process-clinic-letter.form
Mj44 | Forms | Enquiry classification form | P1 | 5 | D | T | All three categories are available, each with a target team, and priority can be set. | Mj27 | S2 | Done | The form the telephone team uses to classify an enquiry and route it. | Case study - classify as admin, finance or clinical and route to the right team | bpm/model/forms/log-enquiry.form; bpm/model/forms/triage-clinical-enquiry.form
Mj45 | Forms | Form validation, binding and accessibility | P0 | 8 | D | Y | Every form has labels, an error message for invalid input, keyboard access and sufficient contrast. | Mj36-44 | S2 | Partly done | Go through every form and check it validates, is bound to the right task, and can be used by everyone. | Brief task 03 - validation, correct variable exchange, accessibility and consistency | bpm/docs/20-accessibility-and-the-forms.md; bpm/screenshots/v16/accessibility-report.json; bpm/screenshots/v16/tasklist-contrast.json; bpm/docs/16-acceptance-criteria.md section 5
Mj46 | Security | Role-based access control | P0 | 8 | L | Y | A role matrix exists, and a test shows a role being refused an action outside its remit. | Mj13 | S2 | Partly done | Decide who can see and do what, so staff only reach what their job needs. | Case study - authenticate users and apply role-based access control | bpm/camunda/application.yaml; bpm/screenshots/v15/rbac-enforcement.txt; bpm/docs/14-feedback-response.md section 1; bpm/docs/16-acceptance-criteria.md section 5
Mj47 | Security | Audit log | P0 | 8 | L | Y | Referral decisions, consent, letter approval and payment requests all appear in the audit record. | Mj46 | S2 | Partly done | Record important actions so we can show who did what and when. | Case study - audit records show user, date, time and nature; ordinary users cannot edit them | bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/tasks/AuditRecordClinicalDecisionWorker.java; bpm/screenshots/v15/users-roles-authorizations.txt; bpm/docs/16-acceptance-criteria.md section 5
Mj48 | Security | Sensitive data protection | P0 | 5 | Y | L | A review of every model, form and worker finds no stored card data and no unprotected external call. | Mj22 | S2 | Done | Make sure we hold no card data or unnecessary financial detail, and that external traffic is protected. | Case study - do not store full card details; protect information exchanged with external services | bpm/docs/09-risk-contingency-and-config-management.md R-17; bpm/docs/08-test-plan.md TC-NFR-01 and TC-NFR-08
Mj49 | Reports | Management reports and query views | P2 | 8 | Y | T | Each requested report can be produced with a date filter, or the gap is recorded as a limitation. | Mj11 | S2 | Done | The reports managers asked for: referral volumes, waiting times, delayed letters, failed payments and so on. | Case study - reports on referrals, waiting times, delays, payments and refunds | bpm/docs/02-status.md (management reporting recorded as a gap)
Mj50 | Testing | Test plan | P0 | 8 | Y | T | The plan covers normal, alternative and exception paths, and states entry and exit criteria. | Mj11 | S1 | Done | Write down what we will test, how, and what counts as a pass. | Brief - a detailed test plan; LO5 requires an appropriate test strategy | bpm/docs/08-test-plan.md
Mj51 | Testing | Test cases and scripts | P0 | 8 | Y | T | Every exception path in the case study has at least one test case linked to it. | Mj50 | S2 | Done | Write the individual test cases, including the ones that are meant to fail. | Brief - create, evaluate and execute test scripts | bpm/docs/08-test-plan.md section 7 (66 cases); bpm/workers/src/test/java/
Mj52 | Testing | End-to-end process testing | P0 | 13 | Y | T | The main pathway, a payment failure and an external service failure have all been run and recorded. | Mj15-33 | S2 | Done | Run the whole pathway from referral to outcome, including the awkward cases. | Brief tasks 02 and 04 - demonstrate normal, alternative and failure scenarios | bpm/screenshots/run-v16-happy-path.log and the seven other run-v16-*.log files; bpm/docs/03-test-record.md section K
Mj53 | Testing | Form and worker testing | P0 | 8 | Y | D | Each form's validation rules and each worker's failure handling have been exercised and recorded. | Mj36-45 | S2 | Done | Check that forms validate correctly and that workers pass variables correctly. | Brief tasks 02 and 03 - evidence of testing for workers and forms | bpm/docs/08-test-plan.md section 7.2 and 7.3; bpm/screenshots/camunda-forms-rendered.png
Mj54 | Testing | Security, audit and accessibility testing | P0 | 8 | Y | D | An unauthorised action is refused, an audit entry is created, and each form is usable by keyboard only. | Mj46-48 | S2 | Partly done | Try to break the rules on purpose and see whether the system stops us. --- v16.0 status note: Audit entries and the 37-form accessibility audit (0 errors, 0 warnings) exist, and RBAC is enforced in the engine. Not met: no unauthorised action is refused as a business outcome (K5.9), contrast is measured on one form rather than all 37, and no keyboard-only or screen-reader pass has been run (bpm/docs/20). | Brief - LO1 accessibility, LO4 security and audit | bpm/screenshots/v16/accessibility-report.json; bpm/screenshots/v16/tasklist-contrast.json; bpm/screenshots/v15/rbac-enforcement.txt
Mj55 | Testing | Defects, regression and test evidence | P0 | 5 | Y | T | Every defect has a status, and a regression run is recorded after the fixes. | Mj52-54 | S2 | Done | Keep a record of what broke, what we fixed, and re-run tests to prove nothing else broke. | Brief - evaluate test results; quality assurance evidence | bpm/docs/08-test-plan.md section 9 (DEF-01 to DEF-23); bpm/screenshots/v16/engine-record.txt
Mj56 | Demo | Demo script and scenarios | P0 | 5 | T | Y | The script covers a normal, an alternative and a failure scenario, and names a speaker for each part. | Mj52 | S2 | Partly done | Agree what we will show, in what order, and who speaks about which part. --- v16.0 status note: RUNBOOK section 4 covers a normal, an alternative and six failure scenarios. Not met: it names no speaker, so the criterion's 'names a speaker for each part' is not satisfied. | Brief task 04 - representative scenarios, and each member explains their own contribution | bpm/RUNBOOK.md section 4; bpm/tools/run_v16.py
Mj57 | Demo | Integration rehearsal | P0 | 5 | T | Y | The full demo runs twice without failure, and every member can explain the parts they did not build. | Mj56 | S2 | Partly done | Run the demo end to end, on one machine, before the real thing. --- v16.0 status note: The eight pathway runs and the six failure-path runs all execute from one documented procedure. Not met: the demo has not been rehearsed twice end to end with all four members present. | Brief task 04 - demonstrate a working integrated initial release | bpm/screenshots/v16/engine-record.txt (defects found by running); bpm/docs/03-test-record.md section K
Mj58 | Submission | Final submission package | P0 | 5 | T | Y | All five deliverables are uploaded, and the submitted commit or tag is named in the submission note. | Mj57 | S2 | Done | Put everything together and upload it to Blackboard, recording which repository version was submitted. | Brief section 3 - models, workers, forms, plans, demo and the repository version | SUBMISSION.md (submission index); repository tag sr2-snapshot

## Workload
Member | Items | SP | Share | Sprint 1 SP | Sprint 2 SP | Items (2nd) | SP (2nd)
T Tommy | 18 | 96 | 24.2 | 39 | 57 | 19 | 127
D Damon | 13 | 99 | 24.9 | 39 | 60 | 11 | 87
Y Young | 13 | 105 | 26.5 | 37 | 68 | 21 | 115
L Lorrey | 14 | 97 | 24.4 | 36 | 61 | 7 | 68
TOTAL | 58 | 397 | 100 | 151 | 246 | 58 | 397