## Sprint 2
Sprint 2: 2026-09-22 → 2026-09-28
Sprint Goal
Complete the pathway: funding → payment and refund → clinic letter → follow-up and enquiry, then secure, test, demonstrate and submit.
Group | Workpackage | Item ID | Content | First Owner | Second Owner | Story Points | Deliverable / Due
G1-1 | Project management | Mj08-Mj10 | Sprint 2 plan, SU2 records, SR2 review and snapshot | T | Y | 13 | Sprint 2 goal and plan, SU2 log, SR2 recording, tag sr2-snapshot due: Day 1 – Day 7
G2-1 | Requirements | Mj12 | Non-functional requirements: security, audit, availability, accessibility | Y | T | 5 | Non-functional section of the requirements list due: Day 1-2
G3-1 | BPMNcore | Mj21 | Funding check and approval, all three funding outcomes | T | L | 8 | Funding model plus one run per funding source due: Day 1-2
G3-2 |  | Mj22 | Payment process and every failure path: declined, cancelled, duplicate | D | L | 13 | Payment model and declined, duplicate and retry runs due: Day 2-3
G3-3 |  | Mj23 | Refund process, approved by finance only | L | T | 8 | Refund model and a run showing the blocked approval due: Day 3
G3-4 |  | Mj24, Mj25 | Chemotherapy cycles and treatment changes; outpatient letter and escalation | T | D | 21 | Cycle review and change models; letter model with day 7, 30 and 90 runs due: Day 2-4
G3-5 |  | Mj26 | Follow-up, cancellation and no-show | L | D | 8 | Follow-up model and the no-slot-within-the-clinical-timeframe run due: Day 4
G3-6 |  | Mj27 | Enquiry classification and routing to admin, finance or clinical | D | T | 8 | Enquiry model and one run per category due: Day 4-5
G4-1 | Workers | Mj31, Mj32 | Payment, laboratory and imaging workers | L | Y | 21 | Two workers plus interface contracts for payment and laboratory results due: Day 1-3
G4-2 |  | Mj33 | Error handling, retry and idempotency across every worker | L | Y | 8 | Forced-failure switches and duplicate-suppression evidence due: Day 3-4
G4-3 |  | Mj35 | Worker unit and integration tests | Y | L | 8 | Green test run, including the failure cases due: Day 4-5
G5-1 | Forms | Mj40, Mj42-Mj44 | Funding, treatment change, letter approval and enquiry forms | D | T | 23 | Four forms plus the variable binding table due: Day 2-4
G5-2 |  | Mj41 | Payment form and status, with no card-data field | D | L | 8 | Payment form, screenshot and the card-data note due: Day 3-4
G5-3 |  | Mj45 | Form validation, binding and accessibility review | D | Y | 8 | Form review checklist with a screenshot per form due: Day 5-6
G6-1 | Security | Mj46, Mj47 | Role-based access control and audit log | L | Y | 16 | Role matrix, audit design and Operate screenshots due: Day 3-5
G6-2 |  | Mj48 | Sensitive data protection | Y | L | 5 | Data-protection note and the secret scan due: Day 5
G7-1 | Reports | Mj49 | Management reports and query views | Y | T | 8 | Report views, or the gap recorded as a limitation due: Day 5-6
G8-1 | Testing | Mj51, Mj55 | Test cases, defect log and the regression run | Y | T | 13 | Test-case set, defect log and regression output due: Day 2-6
G8-2 |  | Mj52 | End-to-end process testing: normal, alternative and failure | Y | T | 13 | Three recorded runs with logs and screenshots due: Day 5-6
G8-3 |  | Mj53, Mj54 | Form, worker, security, audit and accessibility testing | Y | D | 16 | Two result sets with screenshots due: Day 5-6
G9-1 | Demo & submission | Mj56, Mj57 | Demo script and integration rehearsal | T | Y | 10 | Demo script and rehearsal notes due: Day 6-7
G9-2 |  | Mj58 | Final submission package | T | Y | 5 | Blackboard receipt and submission record due: Day 7
Total | [5 empty] | 246 | 33 items · Wave 1 committed 188 SP · Wave 2 stretch 58 SP