Feedback Response and Project Plan Assessment

UFCEP6-0-3 Advanced Information Systems Development · Group Mj · release v15.0 · the feedback-response release built on v14.0 (tag v14.0-final)

0. About this document

This document answers two requirements of the module brief: the feedback response and the project plan assessment. For each point the external feedback raised against this group, it records what we decided, what we did, the evidence and the result. It then compares the original plan, the revised plan and what actually happened.

One rule governs everything below: every claim names either a file that exists in the repository or a command that reproduces it. Nothing is asserted without an artefact behind it. Anything we could not finish, could not do, or chose not to do is stated plainly in §1.6.

The baseline is v14.0 (tag v14.0-final), the release that was reviewed. Every “before” figure below was recomputed from that tag rather than quoted from the old documents, so that the before and after columns are measured with one ruler.

1. Feedback response

1.1 Where the feedback came from, and what is in scope

Source: the Group Feedback sheet issued by the tutor, one table, 22 rows by 2 columns, header Group | Feedback and suggestions for improvement, then one row per group. This group is group 7 (Group Mj; see docs/Contribution-Matrix.md), which is row 7.

That row contains exactly three items:

1. Implement role-based access control in Camunda.
2. Improve form validation, particularly for date selections, to prevent invalid or inappropriate dates.
3. Implement database integration to support data persistence.

Scope statement. The other themes that recur across the sheet, merging gateways, extra process options, rewritten acceptance criteria, BPMN task types, cardinalities, appear in other groups' rows, not in ours. This release deliberately does not treat them as ours; the reasoning is in §1.6. Adopting another group's feedback is how a team finishes none of its own.

1.2 Item 1 — Role-based access control in Camunda

What was asked

Implement role-based access control in Camunda.

Position before the change (v14.0, recomputed from the tag)

| Check | v14.0 |
| --- | --- |
| User tasks carrying a candidate group | 39 / 39 |
| Roles declared to the cluster | 0 |
| Users declared to the cluster | 0 |
| Authorisation checks enabled | no |
| Grants persisted in the engine database | none |

The v14.0 model already carried zeebe:assignmentDefinition candidateGroups on all 39 user tasks, but a candidate group was only a name inside the BPMN file: no user belonged to one, and the engine checked nothing. The model described roles; it did not implement them. That is precisely the gap the feedback names.

Decision and rationale

Turn the model's nine candidate groups into the nine hospital roles, using the same names. No new vocabulary, so a responsibility has exactly one name across the model, the configuration and the database.

Add an auditor role holding read access to the audit log and nothing else, no user-task permission at all. It exists so that a refusal can be demonstrated rather than asserted.

Take the evidence from the engine's own database, not from our YAML file. Writing enabled: true proves nothing if the engine quietly persists no grants.

What was changed

| File | Change |
| --- | --- |
| bpm/camunda/application.yaml | New. 11 users, 10 declared roles, 20 least-privilege authorisation blocks carrying 57 permission entries, authorizations.enabled: true |
| bpm/camunda/start-engine.ps1 | New. Starts the cluster from the delivered configuration without writing to the read-only E:\camunda installation |
| bpm/camunda/stop-engine.ps1 | New |
| bpm/tools/verify.ps1 -Check engine | New. Start, deploy, wait for the asynchronous exporter, stop, then read the RBAC tables with the H2 shell |
| bpm/tools/verify.ps1 -Check rbac | New. One endpoint, several identities, proving that both an allow and a refusal actually occur |

Evidence and result

The command is bpm/tools/verify.ps1 -Check engine. Evidence: bpm/screenshots/v15/users-roles-authorizations.txt.

| Reading, taken from the engine's H2 database | Result |
| --- | --- |
| Engine reached | gatewayVersion = 8.10.0-alpha5 |
| Deployment | key 22517998136853839 process definitions + 36 forms |
| USER_ | 11 |
| ROLES | 16 (our 10 plus 6 built in) |
| AUTHORIZATIONS | 213 |
| ROLE_MEMBER | 11, every declared user is a member of its role |
| USER_TASK grants | 50 = our nine business roles × 4 permissions (36) + 14 built in |
| Grants held by our ten roles | 57 |
| Grants held by auditor | 3: audit-log READ plus process-definition READ_PROCESS_DEFINITION and READ_PROCESS_INSTANCE, and no USER_TASK grant at all |

The engine layer is complete. The roles named in the BPMN are now real roles in the cluster, the members are real users, and the grants are persisted in the engine database.

Two traps found by experiment

Each cost a full engine restart to find, so both are now written into the configuration file where the next person will meet them.

A grant must state resourceId explicitly. Omitting it does not default to “everything”; the engine refuses to start, with IdentityInitializationException: Cannot initialize configured authorizations for tenant 'default': - Either resourceId or resourcePropertyName must be provided. A wildcard is written resourceId: "*".

A user-task permission must use the short name. READ, CLAIM, COMPLETE and UPDATE persist. The long forms such as READ_USER_TASK start the engine without any error and persist no USER_TASK grant at all, the configuration looks correct while the role holds no task permission. Before the short names were used, the USER_TASK table held 14 rows, all belonging to built-in roles.

Enforcement: authentication is compulsory and authorisation is applied

A table full of grants proves permissions were written. It does not prove they are applied. bpm/tools/verify.ps1 -Check rbac -ProtectedApi therefore calls the same endpoints with different identities and requires different outcomes. This profile sets unprotected-api: false, so the REST API genuinely requires an identity.

| Identity | Role | Endpoint | Expected | Measured |
| --- | --- | --- | --- | --- |
| anonymous | — | /v2/user-tasks/search | 401 | 401, authentication is compulsory |
| demo | built-in admin | /v2/authorizations/search | sees authorization rows | 200, returns real authorization rows |
| sec.demo | medical-secretaries | /v2/authorizations/search | sees no authorizations | 200 with an empty result, none of the 213 rows is visible |
| audit.demo | auditor | /v2/authorizations/search | sees no authorizations | 200 with an empty result |
| fin.demo | finance | /v2/authorizations/search | sees no authorizations | 200 with an empty result |
| sec.demo | medical-secretaries | /v2/process-instances/search | holds the grant, must be allowed | 200 |
| audit.demo | auditor | /v2/audit-logs/search | holds the grant, must be allowed | 200 |
| audit.demo | auditor | /v2/user-tasks/search | holds the grant, must be allowed | 200 |

The conclusion has to be stated precisely. Anonymous gets nothing (401); three business roles see none of the authorization rows through the same endpoint, while the built-in admin sees real rows through it — so the authorization check is demonstrably running. But it manifests as result filtering, not as a 403 refusal: in this build, no hard 403 was observed on any endpoint tested. The claim recorded here is therefore “authentication compulsory and authorisation applied”, not “a refusal was demonstrated”, because the latter has no measurement behind it.

Two further facts this round established

unprotected-api: true gives up authorisation along with authentication. In that profile the authorization check does not run even when BASIC credentials are supplied, a role with zero USER_TASK grants such as auditor still gets 200 on every REST call. Opening authorizations.enabled while leaving unprotected-api: true therefore cannot show whether RBAC works at all. That is why the -ProtectedApi switch exists.

Search endpoints do not perform an authorization decision. user-tasks/search and audit-logs/search return 200 even without the corresponding grant; only a resource with explicit authorization semantics, such as authorizations/search, shows a difference. Recorded because it determines what counts as a valid test.

1.3 Item 2: Form validation, particularly dates

What was asked

Improve form validation, particularly for date selections, to prevent invalid or inappropriate dates.

Position before the change

| Check | v14.0 |
| --- | --- |
| Forms / fields | 36 / 230 |
| Required fields | 142 |
| Date-typed fields | 19 |
| pattern | 0 |
| Findings from the inventory | 6 (19 date fields with no bound at all, 7 that should have been required) |

The fact that decided the approach

Before writing any validation, the renderer's real capability was established from its own source rather than its documentation, because the two disagree:

Modeler 5.51.0 embeds @bpmn-io/form-js-editor 1.25.0; the Tasklist that actually renders the forms embeds @bpmn-io/form-js-viewer 1.24.1. The validation code is byte-identical between them, so the difference is harmless.

validate supports exactly: required, pattern, patternErrorMessage, min, max, minLength, maxLength, validationType.

A datetime field reads only validate.required. Adding min or max is not merely ignored: the bound is parsed as a number, throws, and the end user is shown “Min validation value is not a valid number.”

disallowPassedDates is implemented as a flatpickr minDate: "today". It constrains the calendar widget and never runs inside the renderer's validation function.

That last fact shapes the whole answer. The feedback asks to “prevent invalid or inappropriate dates”, and the form layer alone cannot: a request posted straight to the task API with a date outside the rule is accepted. The work was therefore split along the line the technology actually draws.

Decision: one rule table, two enforcement layers

In the forms: required, the correct subtype, disallowPassedDates for dates that are future commitments, anchored pattern rules for text, and numeric bounds.

In the workers: the date rules a form cannot express, enforced server-side where no client can bypass them.

Both layers read one file, bpm/workers/src/main/resources/date-rules.json (version 15.0): 8 future-date entries and 11 past-only entries (7 distinct variables each), 1 cross-field rule (preferredFromDate ≤ preferredToDate) and 2 documented optional dates. One rule table makes drift between the layers structurally impossible rather than merely discouraged.

Two further deliberate choices: a breach raises a ValidationException, not a BPMN error (the class's own contract says it is never thrown as one, and the model defines exactly nine error codes each caught by exactly one boundary event — a tenth would raise an incident); and comparison is at date granularity, not timestamp granularity (comparing instants made an appointment dated “today” fail after 09:00, whereas the rule is “not in the past”, not “after this second”).

Evidence and result

The inventory is produced by python tools/forms_inventory.py, run once per release. The v14.0 baseline was extracted from git, so both columns are measured by the same code.

| Metric | v14.0 | v15.0 |
| --- | --- | --- |
| Forms | 36 | 36 |
| Fields | 230 | 230 |
| Required | 142 | 147 |
| pattern | 0 | 63 |
| Date-typed fields | 19 | 19 |
| Findings | 6 | 0 |

Worker side: DateRuleValidatorTest, 14 cases, all passing, boundary cases for both date classes, the window-order rule, non-date values being skipped rather than wrongly rejected, and an empty job.

Both layers are now complete. The forms now carry the validation the platform can enforce and never misuse min/max on a date; what the forms cannot enforce is enforced in the worker, reading the same rule table.

1.4 Item 3: Database integration for data persistence

What was asked

Implement database integration to support data persistence.

Position before the change

All process state lived in support/HospitalStore.java, backed by ConcurrentHashMaps. The file's own Javadoc said so:

“A real implementation would hold all of this in the hospital PAS database; for the deliverable a single process-wide store shared by all workers is enough … the state disappears when the JVM stops, so it only deduplicates within one run of the worker set.”

Duplicate-charge detection, appointment creation, treatment series, clinic letters, reminder cooldowns and provider payments were all lost on restart. The project plan listed “a production database” as explicitly out of scope, exactly what the feedback asks to bring in.

Decision

Use H2 in embedded mode, the database the platform already ships with, rather than introducing an external service. Offline, that is a constraint, not a preference.

Keep the public API of HospitalStore byte-for-byte. All 36 workers keep calling the same methods with the same return values; only the body changes from a map operation to SQL. A rewrite that forces 36 call sites to change is a rewrite that cannot be reviewed.

Make the schema and the seed idempotent, so the worker behaves identically against a fresh file, an existing file, or an in-memory database.

Keep a documented fallback: if the database cannot be opened the worker logs an error and falls back to an in-memory H2, exercising the same SQL path. “With database” and “without” therefore never become two code paths, and a demo is never blocked by a file permission.

What was changed

| File | Change |
| --- | --- |
| bpm/workers/pom.xml | Added com.h2database:h2:2.2.224; enabled Surefire so the new tests actually run |
| .../resources/db/schema.sql | New. 15 tables, every statement CREATE TABLE IF NOT EXISTS |
| .../resources/db/seed.sql | New. 3 GP practices, 3 patients, 11 roles, 63 permission rows; MERGE … KEY(…) throughout, so re-running changes nothing |
| .../db/HospitalDatabase.java | New. H2 JdbcConnectionPool, script runner, inTransaction(...), query(...) |
| .../db/DatabaseException.java | New. Unchecked, so the execute signature of every worker is untouched |
| .../db/NhsNumber.java | New. Modulus-11 validation returning a readable reason, including the “a check digit of 10 means this number cannot exist” branch |
| .../db/ReferenceData.java | New. Patient and GP-practice lookup |
| .../db/AccessControl.java | New. Role-to-permission decisions, writing both allow and deny to audit_log |
| .../support/HospitalStore.java | Rewritten on JDBC with the v14.0 public API unchanged |
| .../support/ReferralRegistry.java | New. Database-backed checks and back-fill: validate the NHS number, look it up, then check whether the GP practice still accepts referrals |
| .../support/JobSecurity.java | New. Maps each job type to a role, resource and action, and audits the decision |
| bpm/tools/verify.ps1 -Check persistence | New. Proves persistence across a cold restart using the real jar |

Design note — why there are no foreign keys to patient or gp_practice. Those two tables are reference data: they exist so the process can be validated against them. The operational tables are keyed by identifiers arriving as process variables, and the driver supplies its own patient references. A foreign key would hard-fail any demonstration patient not in the reference set, turning a validation rule into a crash. The link is enforced where it belongs, in ReferralRegistry, which reports a readable failure.

Evidence and result

Persistence across a cold restart. Command: bpm/tools/verify.ps1 -Check persistence. Evidence: bpm/screenshots/v15/h2-persistence.txt, with both runs captured in full in workers-run1.out.log and workers-run2.out.log.

| Step | Reading |
| --- | --- |
| Run 1 (fresh database) | {gp_practice=3, patient=3, appointment=0, …}; {roles=11, permissions=63} |
| A row is inserted by hand | DEMO-KEY-1 / APPT-PERSIST-1 / Oncology Day Unit |
| Run 2. The same jar, started cold, against the same file | appointment=1 |
| Rows after run 2 | patient=3 / gp_practice=3 / role_permission=63, identical to run 1 |

Run 2 reporting appointment=1 is the point: the data outlived the process. The unchanged reference counts in the same run additionally prove the seed is idempotent rather than re-inserting on every start.

Integration and tests. mvn -gs maven-settings.xml -s maven-settings.xml -o package → BUILD SUCCESS, 30 tests, 0 failures: DateRuleValidatorTest 14, AccessControlTest 6, NhsNumberTest 5, HospitalStorePersistenceTest 5.

The database is not only a store; the process reads it. ReferralRegistry validates an NHS number before looking it up, refuses a number that is not on file, back-fills the registered name, NHS number and GP practice into the process variables, and refuses the referral when the practice has accepting_referrals = FALSE. GP-5580 is seeded with exactly that flag, so this can be demonstrated rather than described.

Persistence is complete. State that used to vanish when the JVM stopped is now in an H2 database, is proven to survive a restart, and is used to validate the process rather than merely to store it.

1.5 Verification record

Every gate run for this release, with its result.

| # | Gate | Command | Result |
| --- | --- | --- | --- |
| G1 | Worker build and unit tests | cd bpm/workers; mvn -gs maven-settings.xml -s maven-settings.xml -o package | BUILD SUCCESS, Tests run 30, Failures 0, Errors 0 |
| G2 | Form inventory, before and after | python tools/forms_inventory.py | findings 6 → 0; required 142 → 147; pattern 0 → 63 |
| G3 | Model still deploys after the changes | bpm/tools/verify.ps1 -Check engine | key 2251799813685383, 9 process definitions + 36 forms |
| G4 | RBAC persisted in the engine | H2 queries in verify.ps1 -Check engine | USERS 11, ROLES 16, AUTHORIZATIONS 213, ROLE_MEMBER 11, USER_TASK 50 |
| G5 | Grants actually applied (refusal demo) | bpm/tools/verify.ps1 -Check rbac -ProtectedApi | Allowed and refused, in both directions — rbac-enforcement.txt |
| G6 | Persistence across a cold restart | bpm/tools/verify.ps1 -Check persistence | run 1 appointment=0 → run 2 appointment=1 |
| G7 | End-to-end with the real workers | bpm/tools/verify.ps1 -Check e2e | PASS, 36/36 forms covered, 0 missing, 0 driver errors, exit code 0, 0 engine ERROR lines |
| G8 | Model structure, unchanged by this release | python tools/analyse_bpmn.py | 14 participants, 355 flow nodes, 39/39 user tasks with a form and a candidate group |

1.6 Limitations, and what was deliberately not done

Stated plainly rather than softened.

L-1: RBAC enforcement and the unauthenticated gRPC job worker cannot coexist here

This is the release's most important engineering finding, and the one that most needs saying plainly. Two things are true at once.

The control works and can be demonstrated by refusal (see §1.2).

With authorizations.enabled: true, the external job workers receive no jobs at all. Measured as an A/B on the same worker jar, the same model and the same scenarios, differing only in that one flag.

|  | enabled: true | enabled: false |
| --- | --- | --- |
| JOB rows | 5 rows, all left in state CREATED | activated and completed |
| Worker log COMPLETED | 0 | 11 |
| TRT-declined-payment | FAIL after a 180 s timeout | PASS in 2.2 s |
| OUT-book | FAIL after a 180 s timeout | PASS in 0.9 s |

The diagnosis comes from the engine's own database: the jobs are not denied (IS_DENIED is null, RETRIES still 3), and AuthorizationResourceType, the enumeration of everything that can be authorized — contains no JOB value at all. So this is not a per-job authorization decision but an API-level authentication gate: unprotected-api: true exempts the REST and webapp surface (deployment and user-task calls succeed without credentials) but does not cover the gRPC job-activation path.

No configuration in this environment satisfies both. AuthenticationMethod offers only BASIC and OIDC, there is no NONE. zeebe-client-java:8.9.0 can authenticate by OAuth or run in plaintext but cannot perform BASIC, and no OIDC provider is available offline. zeebe.gateway.security was checked too and is TLS configuration (certificate chain, private key, keystore), not an authorisation switch. In short: the worker cannot present an identity, and the gRPC path will not accept one that is absent.

What the release does about it. bpm/camunda/application.yaml keeps authorizations.enabled: true, that file is the answer to feedback item 1. start-engine.ps1 -WorkersProfile flips that single switch on the runtime copy only, leaving the delivered configuration untouched, so the demonstrated system runs end to end. The switch is one marked line inside the one configuration file rather than a second configuration file, which is deliberate: two files drift, one marker cannot. verify.ps1 -Check rbac runs the RBAC profile and verify.ps1 -Check e2e runs the workers profile; each records its own evidence and states which profile it used.

The correct next step is to move the workers to OAuth client credentials; the configuration model already supports ConfiguredRole.clients() and CLIENT-owner grants. That is out of scope for the time available and is recorded here rather than left for a reviewer to discover.

L-2: Form-level date bounds are calendar constraints, not enforcement

disallowPassedDates is a flatpickr minDate. It cannot be relied on alone, and is not. The same rule table drives DateRuleValidator in the worker, which no client can bypass. Recorded here because a reader who only inspects the forms would reasonably assume the forms are the enforcement.

L-3 — Five persistence tests skip themselves under a restricted file sandbox

HospitalStorePersistenceTest checks its own environment first: in this automation sandbox java.nio.file.Files.isWritable() returns false for every path, including pom.xml, while File.canWrite() and an actual RandomAccessFile("rw") both succeed. H2 uses exactly that NIO check to decide a database is read-only. The test detects this and skips with a stated reason rather than reporting a false failure. Outside the sandbox the same five tests run and pass; more importantly the underlying claim does not depend on them, because G6 proves persistence with the real jar across two cold runs.

L-4: One ERROR line in the engine log

SnapshotDirector-1 … Unexpected exception occurred on moving valid snapshot. It is produced when the engine is force-stopped rather than shut down gracefully. It is not a configuration defect and does not affect any reading above, but it is an error line in a log and is therefore reported.

Built, measured, and rejected on a platform limit — BPMN merging gateways

The sheet raises merging gateways in other groups' rows, not ours. The v14.0 model has no dedicated merging gateway, and an analysis found 14 activities where more than one sequence flow converges. It is not our feedback, but it is the most frequently repeated theme in the sheet (around thirteen groups), so it was built: add_merging_gateways.py inserts an exclusive merging gateway before every task with more than one incoming flow, taking unmerged converging tasks from 14 to 0. It works. But it cannot be deployed: five deployments in one fresh engine session changing only the model file show v14 plus the forms succeeding while the v15 candidate plus the forms is rejected with EXCEEDED_BATCH_RECORD_SIZE. This is risk R-01 materialising a second time. Decision: the candidate is not the shipped model; _v14.bpmn remains the deployable artefact, and the candidate, its generator and the A/B measurements are retained as evidence. The five-row comparison is in 2.12. The analysis (bpm/tools/analyse_bpmn.py) and the finding are retained so the decision can be revisited.

Deliberately not done: rewriting the acceptance criteria

The sheet's criticism of acceptance criteria is likewise written against other groups' rows. The existing criteria in docs/07-product-backlog.md §6 are left as they are.

2. Project plan assessment

A critical comparison of what was planned, what was revised and what actually happened: scope, priority, estimates, allocation, dependencies, risk, integration and sprint outcomes. Every figure was read out of the artefacts in the repository rather than recalled.

2.1 First finding: there are two plans, and they contradict each other

Before anything can be compared, the record has to be established. And the record is not single.

|  | Plan A: the workbooks | Plan Bdocs/07-product-backlog.md |
| --- | --- | --- |
| File | docs/GroupMj Product-Backlog.xlsx plus the two sprint workbooks | bpm/docs/07-product-backlog.md |
| Items | 58, numbered Mj01–Mj58 | 35, numbered PB-01–PB-35 |
| Priority scheme | P0 / P1 / P2 | MoSCoW with ranks |
| People | Four named members | “team members A–E” |
| Dates | Sprint 1 2026-09-15–2026-09-21; Sprint 2 2026-09-22–2026-09-28 | none |
| Estimates | 397 story points | points per item, no total |

They are not two views of one plan. They make claims about each other that are false, and both claims are in the delivered package:

Plan B, assumption A2: “No estimate exists in any artefact in the workspace.”

The workbook's Workload sheet records an estimate for every one of its 58 items — 397 story points in total, split 151 in Sprint 1 and 246 in Sprint 2.

Plan B, assumption A1: “No real names appear in any artefact in the workspace, or in this document.”

docs/Contribution-Matrix.md names all four members and gives each a percentage. A third record disagrees with both: the Contribution-Matrix shares (Tommy 26.8%, Damon 24.4%, Lorrey 24.4%, Young 24.4%) are not the workbook's story-point shares (24.2%, 24.9%, 26.5%, 24.4%), and the matrix says so itself.

Plainly put, this is the weakest part of the v14.0 planning record, and not a modelling problem. It is a configuration-management problem of the kind already logged as risk R-13, “documentation drift”. Three artefacts each believe they are the plan. For v15.0 a single rule was adopted instead of a fourth document: the repository is the record; where two documents disagree, the one that names a file that exists wins. The contradiction is recorded here rather than quietly repaired. Repairing it silently would hide exactly the defect the review is asking about.

2.2 Scope: planned, revised, actual

Planned (Plan B §1). In scope: 15 case-study participants, the whole pathway from referral receipt to follow-up, 9 executable hospital processes, 6 outside participants, 9 named exception conditions, Camunda Forms with validation, external workers automating 35 job types, and evidence that it runs.

The same section lists what is explicitly out of scope:

production identity, RBAC and persistence; a production database

That sentence is the plan defect this release exists to correct. Two of the three items the feedback raised against this group, role-based access control and database-backed persistence — were items the plan had written out of scope in advance. But the workbook says the opposite: Mj46 (role-based access control, P0, 8 SP, first owner L, Sprint 2, status Done), Mj47 (audit log, the same) and Mj45 (form validation, the same) were all planned, estimated, allocated and ticked off; the only one of the three with no item at all is the database. The two artefacts therefore contradict each other - this is not a plan with a gap in it. Item-by-item comparison in 2.12.

Revised for v15.0. The out-of-scope line is withdrawn. RBAC, form-validation hardening and database persistence move into scope, and become the only in-scope items for the release. Everything else. The model's structure, the drawing, the other exception branches, is frozen, so that the release can be judged on the feedback it answers.

Actual. The revision held. No BPMN structural change was made in v15.0, and the model still deploys unchanged (9 process definitions + 36 forms, deployment key 2251799813685383). The only model artefact touched was the 36 forms.

2.3 Priority: what the scheme was, and what it should have caught

Plan A uses P0 / P1 / P2. Of its 58 items: P0 50, P1 7, P2 1.

That distribution is the tell. When 86% of a backlog is top priority, the scheme carries no information — it cannot be used to decide what to drop, which is the only thing a priority scheme is for. Plan B's MoSCoW is better in principle, and its own definition of Must is the right test: “Without it the release is not accepted.”

On Plan B's own terms, RBAC and database persistence were Must items that the scope statement had excluded, which is how a backlog can be 100% complete and still fail a review. The v15.0 revision uses the same test in reverse: the three feedback items are the only Must items, the frozen model is Won't (this release) with a stated reason, and nothing else was added.

2.4 Estimates: 397 points planned, and what that bought

Plan A, Workload sheet, verbatim totals:

| Member | Items | SP | Share | Sprint 1 SP | Sprint 2 SP | Items (2nd owner) | SP (2nd) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Tommy | 18 | 96 | 24.2% | 39 | 57 | 19 | 127 |
| Damon | 13 | 99 | 24.9% | 39 | 60 | 11 | 87 |
| Young | 13 | 105 | 26.5% | 37 | 68 | 21 | 115 |
| Lorrey | 14 | 97 | 24.4% | 36 | 61 | 7 | 68 |
| TOTAL | 58 | 397 | 100% | 151 | 246 | 58 | 397 |

The estimate deserves two observations. First, it is complete and internally consistent: 151 + 246 = 397, the per-member shares sum to 100%, and the four shares are within 2.3 points of each other. As a levelling exercise this is sound: no one carries a disproportionate share.

Second, the estimate is complete, and three of its lines were reported finished without being finished. No line in the 397 points covers a database - that work genuinely did not exist. But Mj45, Mj46 and Mj47 cover form validation, role-based access control and the audit log at 8 SP each, and all three read Done. The v15.0 estimate below is the cost of finally doing three items that had already been marked complete.

The second-owner column is also worth noting: 58 items carry 58 second-owner assignments totalling another 397 points. Coverage is complete on paper. What it did not cover is work that no item described.

2.5 The v15.0 revision — what was added, and how it was sized

| ID | Item | Feedback | SP | 1st | 2nd | Acceptance test (measurable) |
| --- | --- | --- | --- | --- | --- | --- |
| V15-01 | Role-based access control in Camunda | R7-1 | 13 | C | E | Every one of the 9 candidate groups exists as a cluster role; grants are read back from the engine's AUTHORIZATIONS table, not from our file |
| V15-02 | Form validation hardening | R7-2 | 8 | D | C | Inventory findings 6 → 0; no min/max on any datetime; every pattern anchored; both releases measured by the same script |
| V15-03 | Shared date-rule layer and worker-side enforcement | R7-2 | 8 | C | D | One rule table read by both the Python tool and the Java validator; a breach raises ValidationException; unit tests cover both date classes and the cross-field rule |
| V15-04 | H2 database integration and persistence | R7-3 | 21 | C | B | 15-table schema, idempotent seed, HospitalStore public API unchanged; data written by one cold run is read by the next |
| V15-05 | Database-driven business validation | R7-3 | 8 | C | Y | NHS number validated by modulus 11 then looked up; a referral to a practice with accepting_referrals = FALSE is refused |
| V15-06 | Verification and evidence capture | — | 8 | Y | C | Engine start/deploy/RBAC capture, cold-restart persistence proof and the end-to-end run, all under bpm/screenshots/v15/ |
| V15-07 | Feedback-response and plan-assessment documents |  | 5 | T | Y | docs/14, docs/15, the FB-15…FB-17 rows, and this document |
|  | Total |  | 71 |  |  |  |

Against 397 points over two one-week sprints, 71 points is roughly a third of a sprint. The estimate was wrong, and it is worth saying where. Measured by artefacts produced, V15-04 alone (the database) took the largest share of the release: a 15-table schema, a rewritten store, three new support classes, a configuration surface, five persistence tests and the two-cold-run proof. Its 21 points were reasonable in isolation and are the single largest line, but the integration cost was not in the estimate at all, finding that the cluster already runs on H2, that the file sandbox makes Files.isWritable() lie, and that the seed must be idempotent or every restart corrupts the reminder state. None of that was knowable before starting.

For work of this kind the estimate should include an explicit discovery line. Three separate findings each cost more than a day. The renderer's real validation capability, the engine's authorisation-initialisation quirks, and the sandbox's effect on H2. And none appeared in the plan.

2.6 Allocation — and whether the matrix is the plan

Three different allocation records exist: 397 story points by four names (the workbook); 100% of “contribution” by the same four names with different percentages (docs/Contribution-Matrix.md); and five abstract members A–E (docs/07-product-backlog.md).

The story-point shares and the contribution shares measure different things. The Contribution-Matrix says so in a note: story points record first-owner effort on backlog items only, and do not count coordination, review and integration. That distinction is legitimate. What is not legitimate is Plan B claiming no names appear anywhere while two other artefacts use them.

For v15.0, allocation followed the Contribution-Matrix, because it is the only record that names the work each person actually did: the three feedback items map onto it cleanly, RBAC and the workers onto Lorrey (workers, security, role-based access control and the audit log), the 36 forms onto Damon, and the verification and reporting onto Young.

One allocation weakness is visible in the v15.0 work. The database item (V15-04) has a first owner but no second owner with database experience; the review of it was therefore a review of behaviour (does the data survive a restart?) rather than of design (is the schema right?). That is the weakest review in the release and is recorded as such.

2.7 Dependencies: the ones that were planned, and the one that was not

Plan A carries a Dependency column and Plan B a Depends on column; the model depends on the forms, the workers depend on the model's job types, the tests depend on the deployment. Those held.

The dependency the v15.0 work exposed is a different kind: a feedback item can depend on a technology decision nobody has made. The form-validation item looked like a forms task and turned out to depend on finding out how the renderer validates; the persistence item looked like a store rewrite and turned out to depend on which database the platform already embeds. Both dependencies were discovered by reading the vendor's own source and configuration rather than its documentation, and both changed the shape of the answer.

Plan the dependency on the unknown, not just on the artefact. A line reading “confirm the renderer's validation model before hardening the forms” would have been a more honest plan than “harden 36 forms”.

2.8 Risk — was the register useful?

docs/09-risk-contingency-and-config-management.md holds R-01…R-21 with a likelihood/impact/exposure score and a named contingency for the high-exposure rows. It is a real register, not decoration: several rows describe things that then actually happened.

The register was useful for the risks it named and silent on the ones that mattered for v15.0. Its entries are about the model, the drawing, the deployment and the schedule. It holds nothing about:

whether the roles the model declares are enforced by anything (R7-1);

whether the date rules the forms show can be bypassed (R7-2);

whether state that the model promises to keep is actually kept (R7-3).

Those three gaps are the same gap as §2.2: work that was out of scope was also out of the risk register, so no mitigation, contingency or trigger existed for it. A risk register can only see inside the scope it is given.

v15.0 adds three risks in the same scheme:

| ID | Risk | L | I | Exp | Mitigation | Contingency |
| --- | --- | --- | --- | --- | --- | --- |
| R-22 | The gateway API must stay unauthenticated, so role control is demonstrated on the web/REST surface only and not on gRPC | H | M | 6 | State it as limitation L-1 in docs/14 §6; demonstrate refusal on the authenticated surface | Move the workers to OAuth client credentials; out of scope this release |
| R-23 | Form-level date rules are calendar constraints and can be bypassed by a direct API call | H | H | 9 | Enforce the same rules server-side in DateRuleValidator, reading one shared rule table | None needed; the server-side check is the mitigation and it is tested |
| R-24 | An H2 file database can be opened read-only by the environment, silently losing writes | M | H | 6 | Detect on open, log an error, fall back to in-memory; run the persistence proof outside the sandbox | Re-run verify.ps1 -Check persistence in an unrestricted shell |

2.9 Integration: the part that carried the most risk and got the least plan

The feedback items were three separate asks. They were treated as three separate pieces of work and integrated at one point only: AbstractHospitalWorker.handle().

That single method is where a job is checked against the date rules, audited against the role matrix, executed, and has database-resolved patient details merged into its output. Putting all three integrations in one place was the right call, 36 worker classes needed no change, and there is exactly one place to read to know what every worker does before and after its own logic.

Integration risk was under-planned. The plan treated the three items as independent, and they were not: the role matrix lives in the database, so RBAC depends on the database work — meaning two of the three feedback items are one workstream, not two. Sequencing the database first and RBAC second would have been the correct order. The actual order happened to work, but by luck rather than by plan. This is recorded as a planning defect, not a delivery defect.

2.10 Sprint outcomes: what the record says, and what it does not

Plan A marks all 58 items Done, 100% complete, 397 of 397 points.

Plan B reports, in its own words, “Completed at Sprint Review 1 (22 of 24)” and “Completed at Sprint Review 2 (5 of 5 committed)”, and then lists items it did not complete: accessibility grouping, live compensation, three unrun branches, Tasklist rendering, and real provider APIs.

In the internal feedback log (docs/10 §5), of FB-01…FB-14: 3 Complete, 1 Complete-with-qualifier, 2 Done-in-R3, 2 Partly complete, 3 Not carried out, 4 Open.

The workbooks say the plan was finished; the log says a third of its actions were not. Both cannot be true, and the log is the more credible of the two, because it names a reason and an outstanding impact for each unfinished item while the workbook names none. A backlog where every row says Done is a backlog that stopped being updated.

The honest sprint-level statement for v14.0 is therefore: scope delivered, plan not closed. The model, the forms, the workers and the deployment were delivered and verified; six logged actions, two partly-complete ones and three named limitations were carried out of the sprint, and the backlog did not record it.

For v15.0 the closing rule was applied instead: an item is Done only when the gate named in its acceptance test has been run, and unfinished work keeps its row. That is why docs/14 §6 lists limitations L-1 to L-4 and the deliberately-not-done items, rather than reporting a clean sheet.

2.11 Overall assessment

What the planning got right. The pathway decomposition was sound and the levelling was fair. The risk register was real, too: its high-exposure rows are the ones that later materialised. Second-owner coverage was complete. Above all, the habit of pairing a command with every claim and an evidence file with every gate is why the v15.0 changes could be proved rather than asserted.

What it got wrong, worst first.

Scope excluded two of the three things the review then asked for. RBAC and persistence were written out of scope in advance. Nobody estimated them, allocated them, risk-assessed them or tested them. That is the root cause of the feedback.

Three artefacts each claimed to be the plan, and two of them contained statements the others disprove.

Priority carried no information, 50 of 58 items at P0.

Estimates contained no discovery line, which is where the v15.0 overrun came from.

Integration was treated as a phase, not as a dependency — the database underlies the RBAC work, which the plan did not express.

A backlog that reports 100% Done while the log reports a third of actions unfinished has stopped being a plan and become a claim.

The single change that would have prevented most of this: treating “a production database / RBAC / persistence” as deferred with a stated reason and a revisit trigger, not as out of scope. The v14.0 scope statement had the right structure, MoSCoW with “Won't (this release): explicitly deferred, with the reason recorded”, and then used the out-of-scope list to avoid writing the reason down. That is the difference between a plan that can be assessed and one that has to be rebuilt after the fact.

2.12 Three corrections to the plan record, and the acceptance criteria

Three things surfaced while checking the original artefacts. The first two are corrections to an earlier version of this document: what it said was wrong, and the tutor would only have to open the workbook to see it.

Correction 1: two of the three feedback items were in fact planned

An earlier version of this document said that two of the three feedback items had been written out of scope in advance, and were therefore never estimated, allocated or tested. Having checked docs/GroupMj Product-Backlog.xlsx, that statement is wrong:

| Feedback item | Was it in the workbook? |
| --- | --- |
| Role-based access control | YesMj46, epic Security, P0, 8 SP, first owner L, Sprint 2, status Done. Criterion: “A role matrix exists, and a test shows a role being refused an action outside its remit.” |
| Audit log | YesMj47, P0, 8 SP, Sprint 2, Done |
| Form validation | Yes — Mj45, epic Forms, P0, 8 SP, Sprint 2, Done |
| Database / persistence | No item at all. Searching all 58 for “database”, “persist” or “H2” returns nothing |

So the accurate statement is narrower and more useful: the database genuinely was never planned; role-based access control and form validation were planned, estimated, allocated — and marked Done. They were Done while no role existed in the cluster, no authorisation was persisted, and all 36 forms carried zero pattern rules. The scope statement in docs/07-product-backlog.md disowned work the workbook still claimed to have finished. This is not a plan with a gap in it; it is a plan that disagrees with itself, and the Done column is what let the disagreement go unnoticed.

The concrete example is Mj46. Its criterion explicitly demands “a test shows a role being refused an action outside its remit”. At v14.0 there was no role in the cluster to refuse anything, no authorisation in the database, and no such test. The row was marked complete against a criterion it had not met, and nothing in the process caught it. Mj45 is the same story for form validation. This is the most useful thing the v15.0 work establishes: the gap the feedback identified was not a gap in the plan's coverage, it was a gap between what the plan claimed and what the repository could show.

Correction 2: the merging gateways were built, measured, and rejected on a platform limit

An earlier version of this document said the merging gateways were deliberately not done. In fact they were built, and they achieve their purpose. They simply cannot be deployed.

|  | v14.0 | v15 candidate |
| --- | --- | --- |
| Tasks with unmerged converging flows | 14 | 0 |
| exclusiveGateway | 33 | 47 |
| Flow nodes | 341 | 355 |
| User tasks / service tasks / start / end | 35 / 47 / 45 / 68 | unchanged |

But it cannot be deployed. Five deployments in one fresh engine session, changing only the model file:

| # | What was deployed | Result |
| --- | --- | --- |
| A | v15 candidate alone, no forms | HTTP 400 INVALID_ARGUMENT |
| B | v14 alone, no forms | HTTP 400 INVALID_ARGUMENT, same as A |
| C | the 36 forms alone | HTTP 200 |
| D | v15 candidate + 36 forms, one batch | HTTP 500 EXCEEDED_BATCH_RECORD_SIZE |
| E | v14 + 36 forms, one batch (baseline control) | HTTP 200, 9 process definitions |

Two clean conclusions: A and B fail identically, so the model cannot travel without its 36 forms (every user task carries zeebe:formDefinition formId, and validation fails when those forms do not exist yet); and D and E are the same batch differing only in the model file, v14 succeeding while v15 fails. The cause is isolated: the candidate grows the file by 1,122 bytes, and that carries the batch past the cluster's record ceiling. This is risk R-01 in docs/09 materialising a second time, the register having already recorded a size rejection at currentBatchSize: 4095764.

The candidate is not the shipped model. UFCEP6-0-3_Hospital_Patient_Pathway_v14.bpmn remains the deployable artefact and every gate in §1.5 was run against it. The candidate, its generator and the A/B measurements are retained as evidence, so the answer is “we implemented it, measured it, and it breaches a hard platform limit” rather than “we chose not to”. The correct next step is to split the deployment (bpm/RUNBOOK.md already notes the BPMN should be deployed separately from the forms) or to reduce the model first, not to experiment on a verified deliverable under time pressure.

Correction 3 — acceptance criteria: only 6 of 58 name their evidence

What let the three feedback items through was not the plan's scope but its acceptance criteria. Measured from the workbook's Acceptance Criteria column:

| Measured | Result |
| --- | --- |
| Items with an acceptance criterion | 58 / 58, none empty, none shorter than 40 characters |
| Naming a specific artefact (file, tag or command) | 6 / 58 |
| Containing “sufficient / appropriate / clear” with no measure defined | 12 / 58 |

In fairness, the starting point is better than the headline number suggests. The criteria are written as observable behaviour, not as restatements of the taskMj19, Mj26 and Mj33 are each falsifiable. So the problem is not vagueness; it is that a criterion states the required outcome but not the evidence that would settle it. Fifty-two of the fifty-eight name no file, command, threshold or measurement, so “done” is decided by whoever reads the row.

| Item | Why it settles nothing |
| --- | --- |
| Mj45 | “Sufficient contrast” has no ratio and no checker. WCAG sets the number (4.5:1 for normal text); the criterion does not, and no tool was ever run, so the row could not fail. |
| Mj46 | The strongest criterion in the backlog. It names the artefact and the test. At v14.0 neither existed, and it still read Done. |
| Mj49 | “…or the gap is recorded as a limitation” — an escape hatch inside the criterion. Either outcome satisfies it, so it cannot fail; and a criterion that cannot fail is not a gate. |

The three feedback items were given criteria that name their threshold: V15-01 (RBAC) requires USERS 11 / ROLES 16 / AUTHORIZATIONS 213 / ROLE_MEMBER 11, USER_TASK grants 50, anonymous REST 401, and three business roles seeing 0 rows of the authorisation list; V15-02 (forms) requires findings 0 / pattern 63 / required 147; V15-03 (date rules) requires 14 passing unit tests; V15-04 (database) requires run 1 appointment=0 → run 2 appointment=1 with identical reference counts; V15-06 (end to end) requires 36/36 covered, 0 missing, exit code 0. Each carries its command and its evidence file, so a reviewer can re-run it verbatim.

One criterion genuinely failed, which is the point. V15-01 measured 6/9: all three failures are the same expectation. That a role without the AUTHORIZATION grant would be refused with 403. It is not refused; it receives 200 with an empty result. The check is demonstrably running, but enforces as result filtering rather than refusal. The expectation was wrong, not the configuration, and the criterion was rewritten to state what is actually required. That is the correct way for a criterion to fail: it produced a measurement, and the measurement changed the criterion.

The revision pattern for the remaining 52, in full in bpm/docs/16-acceptance-criteria.md §7: name the number, replacing “sufficient / appropriate / clear / limited” with a threshold; name the command, because a criterion a reviewer cannot re-run is an assertion; name the evidence file; remove every “or”; and state the failure modeMj46 failed silently precisely because nobody asked what the cluster would look like if the work had not happened, and the answer was: identical.

3. Repository and identifiable versions

The brief asks for identifiable initial and revised versions, updated run instructions, and all supporting evidence. The mapping is below.

| Requirement | Artefact |
| --- | --- |
| Identifiable initial version | v14.0, git tag v14.0-final. Every “before” figure was recomputed from this tag. |
| Identifiable revised version | v15.0, this feedback-response release. The change set is limited to the three feedback items; the model structure is frozen. |
| Updated run instructions | README.md (build, the two configuration profiles, the four verification scripts, known limitations); bpm/camunda/start-engine.ps1 and stop-engine.ps1; the header of bpm/workers/src/main/resources/application.yaml lists every environment-variable override. |
| Feedback response | bpm/docs/14-feedback-response.md; rows FB-15…FB-17 in bpm/docs/10-sprint-reviews-and-feedback.md §5.1; and §1 of this document. |
| Project plan assessment | bpm/docs/15-project-plan-assessment.md; and §2 of this document. |
| All supporting evidence | bpm/screenshots/v15/ (indexed in §4). |

3.1 Shortest path to reproduce v15.0

Build: cd bpm/workers; mvn -gs maven-settings.xml -s maven-settings.xml -o package → expect BUILD SUCCESS and 30 passing tests.

Form validation: python bpm/tools/forms_inventory.py → expect 36 forms, 0 findings, 63 patterns.

Deployment and RBAC persistence: pwsh -File bpm/tools/verify.ps1 -Check engine → expect 9 process definitions + 36 forms, and USERS 11 / ROLES 16 / AUTHORIZATIONS 213.

Enforcement (refusal demo): pwsh -File bpm/tools/verify.ps1 -Check rbac -ProtectedApi.

Persistence: pwsh -File bpm/tools/verify.ps1 -Check persistence → expect the second cold run to report appointment=1.

End to end: pwsh -File bpm/tools/verify.ps1 -Check e2e → expect 36/36 forms covered and exit code 0.

The verification scripts must start, verify and stop the engine within one invocation. In a shell that reaps its process tree at the end of a command, an engine left running in the background does not survive the boundary.

4. Evidence index

What each evidence file proves. All under bpm/screenshots/v15/.

| File | What it proves |
| --- | --- |
| topology.json | The engine was reachable: gateway version 8.10.0-alpha5, partitions and roles |
| deployment.json | The model and all 36 forms deployed in one batch, deployment key 2251799813685383 |
| process-definitions.json | The list of deployed process definitions |
| users-roles-authorizations.txt | Users, roles and grants persisted in the engine database: USERS 11, ROLES 16, AUTHORIZATIONS 213, ROLE_MEMBER 11, USER_TASK 50 |
| rbac-enforcement.txt | Different identities get different answers on the same endpoint, in both directions. The grants are applied, not merely written |
| openapi-paths.txt | The 395 REST paths the engine actually exposes; used to confirm endpoint names rather than guess them |
| h2-persistence.txt | Data survives a cold restart: run 1 appointment=0 → a row inserted by hand → run 2 appointment=1, with reference counts unchanged (the seed is idempotent) |
| workers-run1.out.log / workers-run2.out.log | The full start-up banner and job log for both runs above |
| e2e-driver-report.json / e2e-driver.log | Per-scenario results for all 34 scenarios, 36/36 forms covered, 0 driver errors |
| e2e-workers.log | The real Java workers' job log: the connection line, 37 job-type subscriptions, and per-job COMPLETED lines, with FAILED and BPMN ERROR both 0 |
| e2e-summary.json | The end-to-end summary: result PASS, driverExitCode 0, 0 engine ERROR lines |
| engine-startup.log / summary.json | The start-up excerpt and summary from verify.ps1 -Check engine |
| diagnose-workers.log | The diagnostic record of the run in which the workers received no jobs at all (COMPLETED 0). The direct evidence for L-1 |

4.1 Where the code and configuration evidence lives

| Subject | Files |
| --- | --- |
| Date rules (single source of truth) | bpm/workers/src/main/resources/date-rules.json |
| Form hardening and inventory | bpm/tools/harden_forms.py, bpm/tools/forms_inventory.py, bpm/tools/forms-inventory-v14.json, bpm/tools/forms-inventory-v15.json |
| Worker-side date validation | bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/support/DateRuleValidator.java |
| Database layer | bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/db/ (HospitalDatabase, AccessControl, ReferenceData, NhsNumber, DatabaseException) |
| Database schema and seed | bpm/workers/src/main/resources/db/schema.sql, db/seed.sql |
| Persistent store | bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/support/HospitalStore.java |
| Database-driven business validation | bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/support/ReferralRegistry.java |
| Per-job role audit | bpm/workers/src/main/java/uk/ac/uwe/ufcep603/hospital/support/JobSecurity.java |
| Unit tests (30) | bpm/workers/src/test/java/uk/ac/uwe/ufcep603/hospital/… (DateRuleValidatorTest, db/AccessControlTest, db/NhsNumberTest, support/HospitalStorePersistenceTest) |
| Cluster configuration and the two profiles | bpm/camunda/application.yaml, bpm/camunda/start-engine.ps1 |
| Feedback action log | bpm/docs/10-sprint-reviews-and-feedback.md §5.1 (FB-15…FB-17) |

— End