## Sprint 2
Sprint 2: 2026-09-22 → 2026-09-28
Sprint Goal
Complete the pathway: funding → payment and refund → clinic letter → follow-up and enquiry, then secure, test, demonstrate and submit.
打通完整路径：资金审批 → 支付与退款 → 门诊信件 → 随访与咨询，然后完成安全加固、测试、集成演示与最终提交。
Group 组 | Workpackage 工作包 | Item ID 任务名 | Content 内容 | First Owner 第一负责人 | Second Owner 第二负责人 | Story Points 故事点 | Deliverable / Due 交付物 / 完成日
G1-1 | Project management 项目管理 | Mj08-Mj10 | Sprint 2 plan, SU2 records, SR2 review and snapshot Sprint 2 计划、SU2 记录、SR2 评审与版本快照 | T | Y | 13 | Sprint 2 goal and plan, SU2 log, SR2 recording, tag sr2-snapshot Sprint 2 目标与计划、SU2 记录、SR2 录像、sr2-snapshot 标签 due: Day 1 – Day 7
G2-1 | Requirements 需求类 | Mj12 | Non-functional requirements: security, audit, availability, accessibility 非功能需求：安全、审计、可用性与无障碍 | Y | T | 5 | Non-functional section of the requirements list 需求清单中的非功能需求章节 due: Day 1-2
G3-1 | BPMNcore BPMN 核心 | Mj21 | Funding check and approval, all three funding outcomes 资金核查与批准，覆盖三种资金来源 | T | L | 8 | Funding model plus one run per funding source 资金模型，每种资金来源各一次运行 due: Day 1-2
G3-2 |  | Mj22 | Payment process and every failure path: declined, cancelled, duplicate 支付流程与全部失败路径：拒付、取消、重复支付 | D | L | 13 | Payment model and declined, duplicate and retry runs 支付模型，拒付、重复与重试运行 due: Day 2-3
G3-3 |  | Mj23 | Refund process, approved by finance only 退款流程，仅财务有权批准 | L | T | 8 | Refund model and a run showing the blocked approval 退款模型，含越权批准被拦截的运行 due: Day 3
G3-4 |  | Mj24, Mj25 | Chemotherapy cycles and treatment changes; outpatient letter and escalation 化疗周期与治疗变更；门诊信件与三级上报 | T | D | 21 | Cycle review and change models; letter model with day 7, 30 and 90 runs 周期复查与变更模型；信件模型含第 7、30、90 天运行 due: Day 2-4
G3-5 |  | Mj26 | Follow-up, cancellation and no-show 随访、取消与未出席 | L | D | 8 | Follow-up model and the no-slot-within-the-clinical-timeframe run 随访模型，含临床时限内无可用时段的运行 due: Day 4
G3-6 |  | Mj27 | Enquiry classification and routing to admin, finance or clinical 咨询分类并转交行政、财务或临床 | D | T | 8 | Enquiry model and one run per category 咨询模型，每类各一次运行 due: Day 4-5
G4-1 | Workers Worker 开发 | Mj31, Mj32 | Payment, laboratory and imaging workers 支付、检验与影像 Worker | L | Y | 21 | Two workers plus interface contracts for payment and laboratory results 两个 Worker，以及支付与检验结果的接口约定 due: Day 1-3
G4-2 |  | Mj33 | Error handling, retry and idempotency across every worker 全部 Worker 的错误处理、重试与幂等 | L | Y | 8 | Forced-failure switches and duplicate-suppression evidence 强制失败开关与重复抑制证据 due: Day 3-4
G4-3 |  | Mj35 | Worker unit and integration tests Worker 单元测试与集成测试 | Y | L | 8 | Green test run, including the failure cases 全部通过的测试运行，含失败用例 due: Day 4-5
G5-1 | Forms 表单 | Mj40, Mj42-Mj44 | Funding, treatment change, letter approval and enquiry forms 资金批准、治疗变更、信件批准与咨询表单 | D | T | 23 | Four forms plus the variable binding table 四张表单，以及变量绑定表 due: Day 2-4
G5-2 |  | Mj41 | Payment form and status, with no card-data field 支付表单与状态，不含任何卡数据字段 | D | L | 8 | Payment form, screenshot and the card-data note 支付表单、截图与卡数据说明 due: Day 3-4
G5-3 |  | Mj45 | Form validation, binding and accessibility review 表单验证、绑定与无障碍复查 | D | Y | 8 | Form review checklist with a screenshot per form 逐表检查清单，每张表单附截图 due: Day 5-6
G6-1 | Security 安全与合规 | Mj46, Mj47 | Role-based access control and audit log 基于角色的访问控制与审计日志 | L | Y | 16 | Role matrix, audit design and Operate screenshots 角色权限矩阵、审计设计与 Operate 截图 due: Day 3-5
G6-2 |  | Mj48 | Sensitive data protection 敏感数据保护 | Y | L | 5 | Data-protection note and the secret scan 数据保护说明与密钥扫描 due: Day 5
G7-1 | Reports 管理报表 | Mj49 | Management reports and query views 管理报表与查询视图 | Y | T | 8 | Report views, or the gap recorded as a limitation 报表视图，或把缺口记录为已知限制 due: Day 5-6
G8-1 | Testing 测试 | Mj51, Mj55 | Test cases, defect log and the regression run 测试用例、缺陷日志与回归运行 | Y | T | 13 | Test-case set, defect log and regression output 测试用例集、缺陷日志与回归输出 due: Day 2-6
G8-2 |  | Mj52 | End-to-end process testing: normal, alternative and failure 端到端流程测试：正常、替代与失败路径 | Y | T | 13 | Three recorded runs with logs and screenshots 三次运行的记录、日志与截图 due: Day 5-6
G8-3 |  | Mj53, Mj54 | Form, worker, security, audit and accessibility testing 表单、Worker、安全、审计与无障碍测试 | Y | D | 16 | Two result sets with screenshots 两份结果记录与截图 due: Day 5-6
G9-1 | Demo & submission 演示与提交 | Mj56, Mj57 | Demo script and integration rehearsal 演示脚本与集成预演 | T | Y | 10 | Demo script and rehearsal notes 演示脚本与预演记录 due: Day 6-7
G9-2 |  | Mj58 | Final submission package 最终提交包 | T | Y | 5 | Blackboard receipt and submission record Blackboard 提交回执与提交记录 due: Day 7
Total 合计 | [5 empty] | 246 | 33 items · Wave 1 committed 188 SP · Wave 2 stretch 58 SP