## Product Backlog
ID | Epic | Backlog Item | Priority | SP | First | Second | Acceptance Criteria | Dependency | Sprint | Status | Description | Linked Requirement | Evidence Required
Mj01 | Project Management | Confirm the four-person group | P0 | 1 | T | Y | Approval from the tutor is recorded in writing and stored in the repository. | - | S1 | Done | The brief expects five people. Ask the tutor to approve four, and keep the reply. | Assessment brief, section 1 - group size | Screenshot or email from the tutor, saved in docs/
Mj02 | Project Management | Agree scope, stakeholders and assumptions | P0 | 5 | T | D | A stakeholder list, a scope boundary and a numbered assumption list are agreed by all four. | - | S1 | Done | Read the case study together and agree what we build, who is involved, and what we are guessing. | Case study, closing paragraph | docs/case-study-analysis.md committed
Mj03 | Project Management | Product backlog and Definition of Done | P0 | 5 | T | Y | Every item has a first owner, a second owner, an estimate, acceptance conditions and a dependency. | Mj02 | S1 | Done | Write the full list of work, and agree what 'finished' means on this project. | Brief section 2 - prioritised backlog, shared Definition of Done | This workbook, committed as docs/UFCEP6-0-3_Product-Backlog.xlsx
Mj04 | Project Management | Sprint 1 plan | P0 | 3 | T | Y | A written Sprint goal and a Sprint 1 backlog exist, and the estimate fits our capacity. | Mj03 | S1 | Done | Agree the Sprint 1 goal, how much we can take on, and which items we commit to. | Brief section 2 - each Sprint agrees a goal and a controlled Sprint backlog | docs/sprint-1-plan.md and the Sprint 1 workbook
Mj05 | Project Management | Prepare and record standup 1 (SU1) | P0 | 2 | T | Y | All four members have a written update covering progress, evidence, next step, blocker and handover. | Mj04 | S1 | Done | Every member prepares a short update with evidence before the graded standup. | Brief section 2 - graded standups; attendance alone scores nothing | Filled standup sheet, plus board and commit links
Mj06 | Project Management | Sprint 1 review demo and snapshot | P0 | 5 | T | Y | The BPMN increment runs end to end in front of the tutor, and tag sr1-snapshot is pushed. | Mj04 | S1 | Done | Demonstrate what actually runs at the end of Sprint 1, and freeze that version. | Brief sections 2 and 4 - SR1 is marked on the increment as it stands | Demo recording, tag sr1-snapshot, feedback notes
Mj07 | Project Management | Sprint 1 retrospective | P0 | 2 | T | Y | At least two improvements are agreed, each with an owner and a target Sprint. | Mj06 | S1 | Done | Short meeting after the review: what worked, what did not, what we change next Sprint. | Brief section 2 - retrospective after each review | docs/retrospective-s1.md docs/retrospective-s1.md
Mj08 | Project Management | Sprint 2 plan | P0 | 3 | T | Y | The Sprint 2 goal refers to specific SR1 feedback, and the backlog reflects it. | Mj07 | S2 | Done | Turn the Sprint 1 feedback into a Sprint 2 goal and backlog. | Brief section 2 - feedback from each review must shape the next Sprint | docs/sprint-2-plan.md docs/sprint-2-plan.md
Mj09 | Project Management | Prepare and record standup 2 (SU2) | P0 | 2 | T | Y | All four members have a written update, including any handover. | Mj08 | S2 | Done | Same as SU1, and each member also reports on any handover that happened. | Brief - personal progress, next actions and handover evidence | Filled standup sheet, board and commit links
Mj10 | Project Management | Sprint 2 review (SR2) | P0 | 8 | T | Y | BPMN, workers and forms run together in one demonstration, and tag sr2-snapshot is pushed. | Mj08 | S2 | Done | Present the integrated increment to the tutor and collect feedback. | Brief section 2 - SR2 is marked on the integrated increment | Recording, tag sr2-snapshot, feedback notes and the backlog changes it caused
Mj11 | Requirements | Functional requirements list | P0 | 8 | Y | D | Every requirement has an ID and can be traced to the process step that satisfies it. | Mj02 | S1 | Done | Write the numbered functional requirements the system must satisfy, taken from the case study. | Case study - the closing section asks for functional and non-functional requirements | docs/requirements.md with a traceability column linking to backlog IDs
Mj12 | Requirements | Non-functional requirements | P0 | 5 | Y | T | Each requirement states how it can be tested, not just what it asks for. | Mj11 | S2 | Done | Rules about security, audit trails, availability and accessibility, rather than features. | Case study - access control, audit records, availability, patient accessibility | docs/requirements.md, non-functional section
Mj13 | Requirements | Data and variable dictionary | P0 | 5 | L | D | Every worker input and output appears in the dictionary, and names match the models exactly. | Mj11 | S1 | Done | List every process variable: its name, type, where it comes from and which task uses it. | Brief - process variables must be exchanged correctly between forms, tasks and workers | docs/data-dictionary.md, cross-checked against the deployed models
Mj14 | Requirements | External service interface definitions | P0 | 5 | L | T | Each service has a named input, a named output, and at least one defined failure response. | Mj11 | S1 | Done | Define what we send to and expect back from each simulated external service. | Brief task 02 - explain any simulated external service and its limitations | docs/external-interfaces.md, matching the worker code
Mj15 | BPMN | Multi-pool collaboration diagram | P0 | 5 | L | T | Every participant named in the case study appears in a pool, and each pool has an owner. | Mj13 | S1 | Done | Lay out the participants as separate pools and show the messages that pass between them. | Brief task 01 - use multiple pools where independent participants collaborate | bpmn/collaboration-overview.bpmn committed
Mj16 | BPMN | Referral intake and document check | P0 | 8 | T | D | The model requests missing documents and records the request, and never lets the secretary accept a referral. | Mj15 | S1 | Done | Model what the secretary does: check the referral pack is complete, and chase what is missing. | Case study - the secretary checks completeness but cannot judge clinical suitability | bpmn/referral-intake.bpmn plus a screenshot of the completeness gateway
Mj17 | BPMN | Consultant clinical review | P0 | 8 | T | D | All four outcomes are reachable, and the record shows the reason and the consultant's identity. | Mj16 | S1 | Done | Model the four decisions a consultant can make, and record who decided and why. | Case study - accept, reject, request information or redirect; reason and decision maker must be recorded | bpmn/referral-intake.bpmn plus four test runs, one per outcome
Mj18 | BPMN | New patient appointment booking | P0 | 13 | D | L | Both notification paths work, every contact attempt is recorded, and no appointment is confirmed without a slot. | Mj17 | S1 | Done | Model booking against the external scheduling service, including notification by letter and phone. | Case study - use the external scheduling service; phone as well as letter when the appointment is within two weeks | bpmn/appointment-booking.bpmn plus test runs for letter-only and letter-plus-phone
Mj19 | BPMN | Consent and authorised treatment request | P0 | 8 | Y | D | The process blocks any treatment request that has not been authorised by a clinical role. | Mj18 | S1 | Done | Model recording consent, then creating a treatment request only a clinician can authorise. | Case study - treatment requests must be completed and authorised by a clinical professional | bpmn/treatment-request.bpmn plus a test run showing the blocked path
Mj20 | BPMN | Treatment appointment coordination | P0 | 13 | Y | L | The pending path runs end to end, and repeating the attempt never creates a second booking. | Mj19 | S1 | Done | Model coordinating treatment slots, including what happens when an external service is unavailable. | Case study - hold pending, notify, record retries, and do not create a duplicate booking | bpmn/treatment-booking.bpmn plus a test that retries twice and shows one booking
Mj21 | BPMN | Funding check and approval | P0 | 8 | T | L | All three funding outcomes are reachable and each approval records the four required fields. | Mj20 | S2 | Done | Work out who pays: the hospital, an insurer, or the patient, and record the approval details. | Case study - record the funding body, authorisation number, approved amount and any restrictions | bpmn/funding.bpmn plus test runs for each funding source
Mj22 | BPMN | Payment process | P0 | 13 | D | L | Each failure outcome can be produced, and a retry never produces a second charge. | Mj21 | S2 | Done | Model taking payment through the external provider, including every way it can go wrong. | Case study - declined, cancelled, duplicate and never-completed payments; never charge twice | bpmn/payment.bpmn plus test runs for declined, duplicate and retry
Mj23 | BPMN | Refund process | P1 | 8 | L | T | The model prevents a clinical-only role from approving a refund. | Mj22 | S2 | Done | Model refunds when treatment is cancelled or changed, approved only by finance. | Case study - finance decides refunds; clinical staff cannot approve them without finance authority | bpmn/refund.bpmn plus a test run showing the blocked approval
Mj24 | BPMN | Chemotherapy cycles and treatment changes | P1 | 8 | T | D | A change requested outside the system cannot be processed, and the clinical outcome is recorded. | Mj20 | S2 | Done | Model the review before each cycle, and the formal process for changing a treatment plan. | Case study - clinical review and blood tests before each cycle; changes need a formal authorised request, not an email | bpmn/treatment-change.bpmn plus test runs for a cycle review and a formal change
Mj25 | BPMN | Outpatient letter and escalation | P0 | 13 | T | D | All three escalation levels are reachable and the timer dates can be demonstrated. | Mj19 | S2 | Done | Model writing, approving and sending the letter, and chasing it when it is late. | Case study - letter within seven days; weekly reminder; escalate at one month and three months | bpmn/outpatient-letter.bpmn plus test runs at day 7, day 30 and day 90
Mj26 | BPMN | Follow-up, cancellation and no-show | P1 | 8 | L | D | If no slot matches the clinical timeframe, the case is flagged rather than quietly booked late. | Mj25 | S2 | Done | Model follow-up requests, and what happens when a patient cancels, refuses or does not attend. | Case study - record the event, decide the next step, and refer paid appointments to finance | bpmn/follow-up.bpmn plus a test run for no slot within the clinical timeframe
Mj27 | BPMN | Enquiry classification and routing | P1 | 8 | D | T | A clinical enquiry cannot be closed by a non-clinical role, and every enquiry has a resolution record. | Mj19 | S2 | Done | Model logging a patient enquiry and routing it to admin, finance or clinical. | Case study - the telephone team must not give clinical advice; record time, handler and outcome | bpmn/enquiry.bpmn plus one test run per enquiry type
Mj28 | BPMN | BPMN configuration, deployment and variable mapping | P0 | 5 | L | T | Every model deploys without error, and the variable names match the data dictionary. | Mj15-27 | S1/S2 | Done | Make the models deployable and check the variables line up across models, forms and workers. | Brief task 01 - configure the model for deployment | config/deployment.md and the deployment log
Mj29 | Workers | External scheduling worker | P0 | 8 | L | Y | Given a specialty and priority, it returns at least one slot or a clear 'none available' result. | Mj14 | S1 | Done | A small program that asks the scheduling service for an available slot. | Brief task 02 - workers fetch work, use input variables and return results | workers/scheduling-worker.js plus a log of one successful and one failed lookup
Mj30 | Workers | External communication worker | P0 | 5 | L | Y | The worker returns a delivery status, and a failed call is recorded without stopping the process. | Mj14 | S1 | Done | A worker that sends the letter and records the outcome of a telephone call. | Case study - every contact attempt and its outcome must be recorded | workers/communication-worker.js plus logs for a delivered letter and an unanswered call
Mj31 | Workers | External payment worker | P0 | 13 | L | Y | The worker returns all four fields, and no card number is written to a log or a variable. | Mj14 | S2 | Done | A worker that sends a payment request and returns the provider's answer. | Case study - the provider returns status, reference, date and amount; no full card details | workers/payment-worker.js plus a log check showing no card data
Mj32 | Workers | Laboratory and imaging worker | P1 | 8 | L | Y | The worker returns either a result or an 'unavailable' response, and both are handled. | Mj14 | S2 | Done | A worker that simulates ordering a test and getting a result back. | Case study - blood tests before each chemotherapy cycle | workers/lab-worker.js plus logs for both outcomes
Mj33 | Workers | Error handling, retry and idempotency | P0 | 8 | L | Y | Invalid input and timeout are handled, and running the same job twice produces one booking. | Mj29-32 | S2 | Done | Make the workers behave sensibly when something goes wrong, and never act twice on the same job. | Case study - retry without creating a duplicate booking or a duplicate charge | workers/error-handling.md plus test logs for invalid input, timeout and duplicate delivery
Mj34 | Workers | Worker configuration and secret template | P0 | 3 | L | Y | No credential appears in the source, and a new machine can be configured from the template alone. | Mj29 | S1 | Done | Keep connection settings and credentials out of the code. | Brief task 02 - provide configuration management evidence | config/.env.example and CONTRIBUTING.md plus a secret scan of the repository
Mj35 | Workers | Worker unit and integration tests | P0 | 8 | Y | L | Each worker has at least one passing test for normal and one for failure behaviour. | Mj29-33 | S2 | Done | Automated tests that prove each worker behaves correctly, including when things fail. | Brief task 02 - provide evidence of appropriate testing | Test files in workers/test/ and a saved test run output
Mj36 | Forms | Referral document check form | P0 | 5 | D | T | The form marks each document present or missing, and contains no field judging clinical suitability. | Mj16 | S1 | Done | The form the secretary fills in to record which documents arrived and which are missing. | Case study - the secretary can request missing information but cannot assess clinical suitability | forms/referral-check.form plus a screenshot of the rendered form
Mj37 | Forms | Consultant review form | P0 | 5 | D | T | Decision and reason are mandatory, and the submitting user is captured. | Mj17 | S1 | Done | The form the consultant uses to record the decision, the reason and who they are. | Case study - reason and decision maker identity must be recorded | forms/consultant-review.form plus a screenshot
Mj38 | Forms | Appointment and contact record form | P0 | 8 | D | T | Multiple contact attempts can be recorded against one appointment. | Mj18 | S1 | Done | The form for priority, preferred window and the outcome of each contact attempt. | Case study - record every contact attempt and its result | forms/appointment-contact.form plus a screenshot showing two attempts
Mj39 | Forms | Treatment request form | P0 | 8 | D | T | All six fields are present and validated, and the form cannot be submitted without an authorising clinician. | Mj19 | S1 | Done | The form a clinician completes to authorise treatment. | Case study - the request states treatment, start date, cycles, frequency, reviews and special resources | forms/treatment-request.form plus a screenshot
Mj40 | Forms | Funding approval form | P0 | 5 | D | T | All four fields are captured, and the amount is validated as a positive number. | Mj21 | S2 | Done | The form finance completes to record who is paying and under what conditions. | Case study - record funding body, authorisation number, approved amount and restrictions | forms/funding-approval.form plus a screenshot
Mj41 | Forms | Payment form and status | P0 | 8 | D | L | No field accepts a full card number, and the payment status is shown after submission. | Mj22 | S2 | Done | The payment screen. It must never ask for or store full card details. | Case study - the system must not store full card details | forms/payment.form, a screenshot, and a note explaining how card data is avoided
Mj42 | Forms | Treatment change form | P1 | 5 | D | T | The form captures the authorising clinician and the effect on existing costs. | Mj24 | S2 | Done | The formal form for changing a treatment plan, replacing email and phone requests. | Case study - changes requested by email or phone must not be processed | forms/treatment-change.form plus a screenshot
Mj43 | Forms | Letter approval and admin check form | P0 | 8 | D | T | After clinical approval the clinical fields become read-only, and a letter can be sent back. | Mj25 | S2 | Done | Two steps in one screen: the consultant approves the clinical content, then the secretary checks the administration. | Case study - admin can fix formatting but cannot change clinical meaning; suspected clinical errors go back | forms/letter-approval.form plus a screenshot of the read-only state
Mj44 | Forms | Enquiry classification form | P1 | 5 | D | T | All three categories are available, each with a target team, and priority can be set. | Mj27 | S2 | Done | The form the telephone team uses to classify an enquiry and route it. | Case study - classify as admin, finance or clinical and route to the right team | forms/enquiry.form plus a screenshot
Mj45 | Forms | Form validation, binding and accessibility | P0 | 8 | D | Y | Every form has labels, an error message for invalid input, keyboard access and sufficient contrast. | Mj36-44 | S2 | Done | Go through every form and check it validates, is bound to the right task, and can be used by everyone. | Brief task 03 - validation, correct variable exchange, accessibility and consistency | docs/form-review.md with a checklist per form and screenshots
Mj46 | Security | Role-based access control | P0 | 8 | L | Y | A role matrix exists, and a test shows a role being refused an action outside its remit. | Mj13 | S2 | Done | Decide who can see and do what, so staff only reach what their job needs. | Case study - authenticate users and apply role-based access control | docs/access-control.md with the matrix plus test evidence
Mj47 | Security | Audit log | P0 | 8 | L | Y | Referral decisions, consent, letter approval and payment requests all appear in the audit record. | Mj46 | S2 | Done | Record important actions so we can show who did what and when. | Case study - audit records show user, date, time and nature; ordinary users cannot edit them | Screenshots of audit entries in Operate plus docs/audit-design.md
Mj48 | Security | Sensitive data protection | P0 | 5 | Y | L | A review of every model, form and worker finds no stored card data and no unprotected external call. | Mj22 | S2 | Done | Make sure we hold no card data or unnecessary financial detail, and that external traffic is protected. | Case study - do not store full card details; protect information exchanged with external services | docs/data-protection.md plus the secret scan from PB34
Mj49 | Reports | Management reports and query views | P2 | 8 | Y | T | Each requested report can be produced with a date filter, or the gap is recorded as a limitation. | Mj11 | S2 | Done | The reports managers asked for: referral volumes, waiting times, delayed letters, failed payments and so on. | Case study - reports on referrals, waiting times, delays, payments and refunds | docs/reports.md plus screenshots or a sample export
Mj50 | Testing | Test plan | P0 | 8 | Y | T | The plan covers normal, alternative and exception paths, and states entry and exit criteria. | Mj11 | S1 | Done | Write down what we will test, how, and what counts as a pass. | Brief - a detailed test plan; LO5 requires an appropriate test strategy | docs/test-plan.md docs/test-plan.md
Mj51 | Testing | Test cases and scripts | P0 | 8 | Y | T | Every exception path in the case study has at least one test case linked to it. | Mj50 | S2 | Done | Write the individual test cases, including the ones that are meant to fail. | Brief - create, evaluate and execute test scripts | docs/test-cases.md and the automated tests from PB35
Mj52 | Testing | End-to-end process testing | P0 | 13 | Y | T | The main pathway, a payment failure and an external service failure have all been run and recorded. | Mj15-33 | S2 | Done | Run the whole pathway from referral to outcome, including the awkward cases. | Brief tasks 02 and 04 - demonstrate normal, alternative and failure scenarios | docs/e2e-results.md with logs and screenshots for each scenario
Mj53 | Testing | Form and worker testing | P0 | 8 | Y | D | Each form's validation rules and each worker's failure handling have been exercised and recorded. | Mj36-45 | S2 | Done | Check that forms validate correctly and that workers pass variables correctly. | Brief tasks 02 and 03 - evidence of testing for workers and forms | docs/form-worker-test-results.md docs/form-worker-test-results.md
Mj54 | Testing | Security, audit and accessibility testing | P0 | 8 | Y | D | An unauthorised action is refused, an audit entry is created, and each form is usable by keyboard only. | Mj46-48 | S2 | Done | Try to break the rules on purpose and see whether the system stops us. | Brief - LO1 accessibility, LO4 security and audit | docs/security-accessibility-results.md with screenshots
Mj55 | Testing | Defects, regression and test evidence | P0 | 5 | Y | T | Every defect has a status, and a regression run is recorded after the fixes. | Mj52-54 | S2 | Done | Keep a record of what broke, what we fixed, and re-run tests to prove nothing else broke. | Brief - evaluate test results; quality assurance evidence | docs/defect-log.md and the regression run output
Mj56 | Demo | Demo script and scenarios | P0 | 5 | T | Y | The script covers a normal, an alternative and a failure scenario, and names a speaker for each part. | Mj52 | S2 | Done | Agree what we will show, in what order, and who speaks about which part. | Brief task 04 - representative scenarios, and each member explains their own contribution | docs/demo-script.md docs/demo-script.md
Mj57 | Demo | Integration rehearsal | P0 | 5 | T | Y | The full demo runs twice without failure, and every member can explain the parts they did not build. | Mj56 | S2 | Done | Run the demo end to end, on one machine, before the real thing. | Brief task 04 - demonstrate a working integrated initial release | docs/rehearsal-notes.md with the issues found
Mj58 | Submission | Final submission package | P0 | 5 | T | Y | All five deliverables are uploaded, and the submitted commit or tag is named in the submission note. | Mj57 | S2 | Done | Put everything together and upload it to Blackboard, recording which repository version was submitted. | Brief section 3 - models, workers, forms, plans, demo and the repository version | Blackboard receipt and docs/submission-record.md

## Workload
Member | Items | SP | Share | Sprint 1 SP | Sprint 2 SP | Items (2nd) | SP (2nd)
T Tommy | 18 | 96 | 24.2 | 39 | 57 | 19 | 127
D Damon | 13 | 99 | 24.9 | 39 | 60 | 11 | 87
Y Young | 13 | 105 | 26.5 | 37 | 68 | 21 | 115
L Lorrey | 14 | 97 | 24.4 | 36 | 61 | 7 | 68
TOTAL | 58 | 397 | 100 | 151 | 246 | 58 | 397