## Sprint 1
Sprint 1: 2026-09-15 → 2026-09-21
Sprint Goal
Deliver the core end-to-end path: referral intake → document check → consultant review → acceptance → new patient appointment → treatment request.
Group | Workpackage | Item ID | Content | First Owner | Second Owner | Story Points | Deliverable / Due
G1-1 | Project management | Mj01, Mj03-Mj07 | Project kickoff, backlog, SU1/SR1 records, retrospective | T | Y | 18 | Charter, backlog workbook v1.0, SU1/SR1 logs, retrospective minutes due: Day 1 – Day 6-7
G1-2 |  | Mj02 | Scope boundary, stakeholder map, assumption list | T | D | 5 | Scope section, stakeholder map, numbered assumptions due: Day 1-2
G2-1 | Requirements | Mj11 | Functional requirements list and traceability | Y | D | 8 | FRS with traceability to backlog IDs due: Day 1-2
G2-2 |  | Mj13 | Data and variable dictionary | L | D | 5 | Data dictionary cross-checked against models due: Day 2
G2-3 |  | Mj14 | External service interface definitions | L | T | 5 | Interface contracts for four simulated services due: Day 5
G3-1 | BPMNcore | Mj15, Mj28 | Multi-pool collaboration diagram and deployment configuration | L | T | 10 | Collaboration model + deployable configuration package due: Day 3-4
G3-2 |  | Mj16, Mj17 | Referral intake and consultant clinical review | T | D | 16 | Referral process model, four review outcomes testable due: Day 3-4
G3-3 |  | Mj18 | New patient appointment booking and patient notification | D | L | 13 | Appointment model incl. two-week telephone rule due: Day 4-5
G3-4 |  | Mj19 | Informed consent and authorised treatment request | Y | D | 8 | Consent capture + clinician-only authorisation gate due: Day 4-5
G3-5 |  | Mj20 | Treatment appointment coordination | Y | L | 13 | Treatment booking model incl. service-unavailable pending path due: Day 5
G4-1 | Worker | Mj29, Mj30, Mj34 | Scheduling and communication workers, environment configuration | L | Y | 16 | Two workers + secret and configuration templates due: Day 1-4
G5-1 | Forms | Mj36-Mj39 | Core Camunda forms | D | T | 26 | Four forms + variable binding table due: Day 2-5
G6-1 | Test plan | Mj50 | Test plan | Y | T | 8 | Master test plan covering normal, alternative and exception paths due: Day 1-5
Total | [5 empty] | 151 | 25 items · Wave 1 committed 125 SP · Wave 2 stretch 26 SP